## DASHBOARD
🏗️ CONSTRUCTION PMO PERFORMANCE DASHBOARD
RISK DISTRIBUTION
CONTRACTOR PERFORMANCE
IMPROVEMENT AREAS
TOP 10 COST OVERRUNS
PHASE RISK BREAKDOWN (OVERRUNS)
TOTAL PROJECTS
50
TOTAL COST OVERRUN
AVERAGE DELAY_MONTHS
HIGH RISK PROJECTS
6
10
#15.1B
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Project's Status
Contractor's Category
Causation
MONSURU ADELEKE
Email -- adelekemonsuru840@gmail.com
Linked In -- www.linkedin.com/in/adeleke-monsuru
GitHub -- https://github.com/Shile-tech/Construction_PMO_Analytics

## CALCULATIONS
TOP 10 PROJECTS BY COST OVERRUN
status | (All)
overrun_perc
PRJ-042 | 31.68
PRJ-007 | 33.4
PRJ-031 | 36.46
PRJ-045 | 45.39
PRJ-021 | 45.92
PRJ-027 | 47.76
PRJ-033 | 50.55
PRJ-026 | 51.14
PRJ-004 | 53.39
PRJ-005 | 54.11
Grand Total | 449.8
TOTAL COST OVERRUN BY PHASE
total_phase_overrun_NGN
Construction | 5332441000
Procurement | 1393739000
Testing & Commissioning | 888446000
Design | 879441000
Mobilisation | 675478000
Handover | 468754000
Grand Total | 9638299000
CONTRACTOR'S PERFORMANCE
score_categ | (All)
perfom_score %
Horizon Builders | 25.7
Fedex Const. Co. | 29.09
Pioneer Builders Ltd | 29.82
Mainland Const. Co. | 30.85
Greenfield Eng Ltd | 32.44
Nile Construction | 33.83
BuildRight Nig Ltd | 36.49
Tetrazzini & Sons Ltd | 36.79
Apex Infra Ltd | 52.07
Grandeur Works | 53.04
Grand Total | 360.12
PROJECTS RISKS FLAG
status | (All)
Row Labels | Count of project_id
High Risk | 12.24%
Low Risk | 14.29%
Moderate Risk | 73.47%
Grand Total | 100%
IMPROVEMENT AREAS BASED ON HIGH RISK PROJECTS
dimension | (All)
Count of high_risk_count
Abuja | 1
Adverse weather | 1
AECOM Nigeria | 1
Bridge | 1
CCECC Consult | 1
Community protest | 1
Culvert | 1
Delta | 1
Design changes | 1
Drainage System | 1
Enugu | 1
Equipment breakdown | 1
Erosion Control | 1
Kano | 1
Labour dispute | 1
Rivers | 1
School Block | 1
Scott Wilson | 1
Grand Total | 18
Count of Project_ID
50
Sum of Cost_Overrun_NGN
15082331000
Average of Schedule_Delay_Months
10.44

## Q1_Cost_Overrun
TOP 10 PROJECTS BY COST AND SCHEDULED DELAY OVERRUN
s/n | project_id | project_name | budget_NGN | cost_overrun_NGN | overrun_perc | sched_delay_months | status
1 | PRJ-026 | Rivers Hospital Phase 3 | 1861586000 | 952091000 | 51.14 | 4 | Delayed
2 | PRJ-021 | Lagos Bridge Phase 2 | 1856416000 | 852499000 | 45.92 | 6 | Ongoing
3 | PRJ-027 | Anambra Housing Estate Phase 3 | 1767685000 | 844179000 | 47.76 | 7 | Ongoing
4 | PRJ-005 | Kano Erosion Control Phase 2 | 1557483000 | 842805000 | 54.11 | 16 | Ongoing
5 | PRJ-033 | Enugu Bridge Phase 1 | 1511481000 | 763991000 | 50.55 | 16 | Ongoing
6 | PRJ-031 | Anambra Hospital Phase 3 | 1892849000 | 690155000 | 36.46 | 8 | Ongoing
7 | PRJ-045 | Rivers Culvert Phase 3 | 1515965000 | 688123000 | 45.39 | 16 | Ongoing
8 | PRJ-007 | Rivers Housing Estate Phase 1 | 1979571000 | 661176000 | 33.4 | 7 | Ongoing
9 | PRJ-042 | Rivers Housing Estate Phase 2 | 1968675000 | 623606000 | 31.68 | 5 | Ongoing
10 | PRJ-004 | Edo School Block Phase 2 | 1095645000 | 584931000 | 53.39 | 2 | Ongoing

## Q2_Phase_Risk
TOTAL COST OVERRUN BY PHASE
s/n | phase | total_projects | total_phase_overrun | avg_overrun_perct
1 | Procurement | 50 | 1393739000 | 24.086
2 | Mobilisation | 50 | 675478000 | 23.02
3 | Design | 50 | 879441000 | 22.276
4 | Testing & Commissioning | 50 | 888446000 | 19.382
5 | Handover | 50 | 468754000 | 18.636
6 | Construction | 50 | 5332441000 | 17.51

## Q3_Contractor_Performance
CONTRACTOR'S PERFORMANCE
s/n | contractor | total_project | avg_cost_overrun_pct | avg_dur_overrun_perc | perfom_score | score_categ
1 | Grandeur Works | 6 | 18.8 | 28.16 | 53.04 | Average
2 | Apex Infra Ltd | 2 | 21.6 | 26.33 | 52.07 | Average
3 | Tetrazzini & Sons Ltd | 4 | 33.2 | 30.01 | 36.79 | Average
4 | BuildRight Nig Ltd | 6 | 32.9 | 30.61 | 36.49 | Average
5 | Nile Construction | 4 | 21.2 | 44.97 | 33.83 | Poor
6 | Greenfield Eng Ltd | 5 | 28 | 39.56 | 32.44 | Poor
7 | Mainland Const. Co. | 3 | 19.1 | 50.05 | 30.85 | Poor
8 | Pioneer Builders Ltd | 8 | 42.5 | 27.68 | 29.82 | Poor
9 | Fedex Const. Co. | 2 | 22.1 | 48.81 | 29.09 | Poor
10 | Horizon Builders | 10 | 31.4 | 42.9 | 25.7 | Poor

## Q4_Risk_Flags
PROJECTS RISKS FLAG
s/n | project_id | project_name | contractor | budget_NGN | cost_overrun_NGN | perc_cost_overrun | planned_dur_months | sched_delay_months | perc_dur_overrun | perct_completed | status | risk_score | risk_variation
1 | PRJ-012 | Abuja School Block Phase 1 | Pioneer Builders Ltd | 934761000 | 488216000 | 52.23 | 28 | 19 | 67.86 | 52 | Ongoing | 60.05 | High Risk
2 | PRJ-005 | Kano Erosion Control Phase 2 | BuildRight Nig Ltd | 1557483000 | 842805000 | 54.11 | 26 | 16 | 61.54 | 78 | Ongoing | 57.83 | High Risk
3 | PRJ-032 | Delta Drainage System Phase 3 | Fedex Const. Co. | 761070000 | 388034000 | 50.99 | 14 | 9 | 64.29 | 56 | Ongoing | 57.64 | High Risk
4 | PRJ-015 | Rivers Drainage System Phase 3 | Greenfield Eng Ltd | 566860000 | 268385000 | 47.35 | 39 | 26 | 66.67 | 99 | Ongoing | 57.01 | High Risk
5 | PRJ-033 | Enugu Bridge Phase 1 | Horizon Builders | 1511481000 | 763991000 | 50.55 | 27 | 16 | 59.26 | 52 | Ongoing | 54.91 | High Risk
6 | PRJ-045 | Rivers Culvert Phase 3 | Greenfield Eng Ltd | 1515965000 | 688123000 | 45.39 | 29 | 16 | 55.17 | 96 | Ongoing | 50.28 | High Risk
7 | PRJ-034 | Enugu Drainage System Phase 1 | Grandeur Works | 360436000 | 133638000 | 37.08 | 36 | 22 | 61.11 | 90 | Ongoing | 49.09 | Moderate Risk
8 | PRJ-036 | Delta Retaining Wall Phase 1 | Horizon Builders | 274916000 | 146321000 | 53.22 | 23 | 9 | 39.13 | 63 | Ongoing | 46.17 | Moderate Risk
9 | PRJ-009 | Rivers Culvert Phase 1 | Pioneer Builders Ltd | 1502729000 | 410826000 | 27.34 | 39 | 25 | 64.1 | 81 | Ongoing | 45.72 | Moderate Risk
10 | PRJ-041 | Rivers Culvert Phase 1 | BuildRight Nig Ltd | 1344515000 | 432338000 | 32.16 | 17 | 10 | 58.82 | 60 | Ongoing | 45.49 | Moderate Risk
11 | PRJ-037 | Delta Erosion Control Phase 1 | Nile Construction | 1232107000 | 316471000 | 25.69 | 36 | 23 | 63.89 | 54 | Ongoing | 44.79 | Moderate Risk
12 | PRJ-026 | Rivers Hospital Phase 3 | Pioneer Builders Ltd | 1861586000 | 952091000 | 51.14 | 12 | 4 | 33.33 | 42 | Delayed | 42.23 | Moderate Risk
13 | PRJ-044 | Kaduna Drainage System Phase 3 | Horizon Builders | 668731000 | 269599000 | 40.32 | 40 | 17 | 42.5 | 94 | Ongoing | 41.41 | Moderate Risk
14 | PRJ-050 | Edo Drainage System Phase 1 | Horizon Builders | 1204191000 | 418817000 | 34.78 | 17 | 8 | 47.06 | 47 | Delayed | 40.92 | Moderate Risk
15 | PRJ-006 | Rivers School Block Phase 3 | Nile Construction | 1356842000 | 503513000 | 37.11 | 16 | 7 | 43.75 | 51 | Ongoing | 40.43 | Moderate Risk
16 | PRJ-011 | Delta Hospital Phase 2 | Mainland Const. Co. | 540258000 | 152318000 | 28.19 | 12 | 6 | 50 | 44 | Delayed | 39.09 | Moderate Risk
17 | PRJ-020 | Kano Housing Estate Phase 3 | Horizon Builders | 872669000 | 102213000 | 11.71 | 27 | 17 | 62.96 | 39 | Delayed | 37.34 | Moderate Risk
18 | PRJ-031 | Anambra Hospital Phase 3 | Tetrazzini & Sons Ltd | 1892849000 | 690155000 | 36.46 | 21 | 8 | 38.1 | 77 | Ongoing | 37.28 | Moderate Risk
19 | PRJ-048 | Edo Road Construction Phase 3 | Grandeur Works | 1888346000 | 243913000 | 12.92 | 36 | 22 | 61.11 | 83 | Ongoing | 37.02 | Moderate Risk
20 | PRJ-021 | Lagos Bridge Phase 2 | Horizon Builders | 1856416000 | 852499000 | 45.92 | 22 | 6 | 27.27 | 91 | Ongoing | 36.59 | Moderate Risk
21 | PRJ-013 | Anambra Water Treatment Plant Phase 1 | Mainland Const. Co. | 779132000 | 36564000 | 4.69 | 45 | 29 | 64.44 | 71 | Ongoing | 34.56 | Moderate Risk
22 | PRJ-029 | Oyo Water Treatment Plant Phase 1 | Mainland Const. Co. | 447015000 | 147758000 | 33.05 | 28 | 10 | 35.71 | 62 | Ongoing | 34.38 | Moderate Risk
23 | PRJ-027 | Anambra Housing Estate Phase 3 | Pioneer Builders Ltd | 1767685000 | 844179000 | 47.76 | 35 | 7 | 20 | 86 | Ongoing | 33.88 | Moderate Risk
24 | PRJ-008 | Enugu Road Construction Phase 3 | Grandeur Works | 461417000 | 237974000 | 51.57 | 32 | 5 | 15.63 | 93 | Ongoing | 33.6 | Moderate Risk
25 | PRJ-018 | Kano Culvert Phase 1 | Horizon Builders | 1173613000 | 112430000 | 9.58 | 42 | 24 | 57.14 | 54 | Ongoing | 33.36 | Moderate Risk
26 | PRJ-024 | Anambra Road Construction Phase 3 | BuildRight Nig Ltd | 1210318000 | 429817000 | 35.51 | 27 | 8 | 29.63 | 61 | Ongoing | 32.57 | Moderate Risk
27 | PRJ-042 | Rivers Housing Estate Phase 2 | Tetrazzini & Sons Ltd | 1968675000 | 623606000 | 31.68 | 16 | 5 | 31.25 | 54 | Ongoing | 31.46 | Moderate Risk
28 | PRJ-022 | Rivers Road Construction Phase 1 | Grandeur Works | 567146000 | 238452000 | 42.04 | 41 | 8 | 19.51 | 92 | Ongoing | 30.77 | Moderate Risk
29 | PRJ-004 | Edo School Block Phase 2 | Pioneer Builders Ltd | 1095645000 | 584931000 | 53.39 | 36 | 2 | 5.56 | 67 | Ongoing | 29.48 | Moderate Risk
30 | PRJ-010 | Anambra Drainage System Phase 1 | Greenfield Eng Ltd | 1729151000 | 72114000 | 4.17 | 22 | 12 | 54.55 | 84 | Ongoing | 29.36 | Moderate Risk
31 | PRJ-003 | Rivers Road Construction Phase 2 | Grandeur Works | 353185000 | 185185000 | 52.43 | 33 | 2 | 6.06 | 78 | Ongoing | 29.25 | Moderate Risk
32 | PRJ-028 | Edo Water Treatment Plant Phase 1 | Horizon Builders | 633789000 | 220580000 | 34.8 | 20 | 4 | 20 | 43 | Delayed | 27.4 | Moderate Risk
33 | PRJ-023 | Kano Water Treatment Plant Phase 1 | Tetrazzini & Sons Ltd | 168867000 | 23331000 | 13.82 | 15 | 6 | 40 | 94 | Ongoing | 26.91 | Moderate Risk
34 | PRJ-039 | Delta Water Treatment Plant Phase 3 | Nile Construction | 1131104000 | 73639000 | 6.51 | 36 | 17 | 47.22 | 52 | Ongoing | 26.86 | Moderate Risk
35 | PRJ-040 | Delta Water Treatment Plant Phase 3 | Horizon Builders | 609482000 | 126731000 | 20.79 | 32 | 10 | 31.25 | 86 | Ongoing | 26.02 | Moderate Risk
36 | PRJ-007 | Rivers Housing Estate Phase 1 | Greenfield Eng Ltd | 1979571000 | 661176000 | 33.4 | 47 | 7 | 14.89 | 71 | Ongoing | 24.14 | Moderate Risk
37 | PRJ-049 | Edo Retaining Wall Phase 2 | Apex Infra Ltd | 582224000 | 140540000 | 24.14 | 36 | 8 | 22.22 | 81 | Ongoing | 23.18 | Moderate Risk
38 | PRJ-030 | Oyo Hospital Phase 3 | Tetrazzini & Sons Ltd | 1553682000 | 516239000 | 33.23 | 28 | 3 | 10.71 | 86 | Ongoing | 21.97 | Moderate Risk
39 | PRJ-038 | Lagos Hospital Phase 3 | Horizon Builders | 760232000 | -6094000 | 0 | 33 | 14 | 42.42 | 45 | Delayed | 21.21 | Moderate Risk
40 | PRJ-043 | Kano Hospital Phase 2 | Fedex Const. Co. | 1567920000 | 127479000 | 8.13 | 45 | 15 | 33.33 | 61 | Ongoing | 20.73 | Moderate Risk
41 | PRJ-002 | Kano Bridge Phase 2 | Apex Infra Ltd | 101745000 | 7051000 | 6.93 | 46 | 14 | 30.43 | 87 | Ongoing | 18.68 | Low Risk
42 | PRJ-047 | Kano Drainage System Phase 3 | BuildRight Nig Ltd | 695219000 | 159591000 | 22.96 | 15 | 2 | 13.33 | 83 | Ongoing | 18.14 | Low Risk
43 | PRJ-014 | Enugu Bridge Phase 3 | Pioneer Builders Ltd | 519700000 | 150928000 | 29.04 | 17 | 1 | 5.88 | 92 | Ongoing | 17.46 | Low Risk
44 | PRJ-025 | Edo Road Construction Phase 2 | BuildRight Nig Ltd | 1152193000 | 161102000 | 13.98 | 28 | 4 | 14.29 | 70 | Ongoing | 14.13 | Low Risk
45 | PRJ-035 | Enugu Culvert Phase 2 | Pioneer Builders Ltd | 96146000 | 6334000 | 6.59 | 33 | 6 | 18.18 | 38 | Delayed | 12.38 | Moderate Risk
46 | PRJ-046 | Oyo Housing Estate Phase 2 | Greenfield Eng Ltd | 507262000 | 76855000 | 15.15 | 46 | 3 | 6.52 | 49 | Delayed | 10.84 | Moderate Risk
47 | PRJ-001 | Lagos Bridge Phase 1 | Pioneer Builders Ltd | 322099000 | 3703000 | 1.15 | 46 | 3 | 6.52 | 84 | Ongoing | 3.83 | Low Risk
48 | PRJ-017 | Lagos Housing Estate Phase 3 | BuildRight Nig Ltd | 181431000 | -5652000 | 0 | 33 | 2 | 6.06 | 60 | Ongoing | 3.03 | Low Risk
49 | PRJ-019 | Enugu Hospital Phase 1 | Grandeur Works | 1734482000 | -30349000 | 0 | 18 | 1 | 5.56 | 73 | Ongoing | 2.78 | Low Risk

## Q5_Improvement_Areas
IMPROVEMENT AREAS BASED ON HIGH RISK PROJECTS
s/n | category | dimension | high_risk_count | avg_risk_score
1 | CCECC Consult | Consultant | 3 | 55.08
2 | AECOM Nigeria | Consultant | 2 | 57.73
3 | Scott Wilson | Consultant | 1 | 57.01
4 | Adverse weather | Delay Reason | 2 | 57.33
5 | Community protest | Delay Reason | 1 | 54.91
6 | Design changes | Delay Reason | 1 | 57.83
7 | Equipment breakdown | Delay Reason | 1 | 50.28
8 | Labour dispute | Delay Reason | 1 | 60.05
9 | Drainage System | Project Type | 2 | 57.33
10 | Erosion Control | Project Type | 1 | 57.83
11 | School Block | Project Type | 1 | 60.05
12 | Bridge | Project Type | 1 | 54.91
13 | Culvert | Project Type | 1 | 50.28
14 | Rivers | State | 2 | 53.64
15 | Abuja | State | 1 | 60.05
16 | Delta | State | 1 | 57.64
17 | Enugu | State | 1 | 54.91
18 | Kano | State | 1 | 57.83

## Projects (cleaned data)
Project_ID | Project_Name | Project_Type | State | Contractor | Consultant | Year_Start | Budget_NGN | Actual_Cost_NGN | Cost_Overrun_NGN | Planned_Duration_Months | Actual_Duration_Months | Schedule_Delay_Months | Pct_Complete | Primary_Delay_Reason | Status
PRJ-001 | Lagos Bridge Phase 1 | Bridge | Lagos | Pioneer Builders Ltd | Mott McDonald | 2020 | 322099000 | 325802000 | 3703000 | 46 | 49 | 3 | 84 | Poor site supervision | Ongoing
PRJ-002 | Kano Bridge Phase 2 | Bridge | Kano | Apex Infra Ltd | Scott Wilson | 2023 | 101745000 | 108796000 | 7051000 | 46 | 60 | 14 | 87 | Permit issues | Ongoing
PRJ-003 | Rivers Road Construction Phase 2 | Road Construction | Rivers | Grandeur Works | Julius Berger Consult | 2021 | 353185000 | 538370000 | 185185000 | 33 | 35 | 2 | 78 | Material price escalation | Ongoing
PRJ-004 | Edo School Block Phase 2 | School Block | Edo | Pioneer Builders Ltd | AECOM Nigeria | 2022 | 1095645000 | 1680576000 | 584931000 | 36 | 38 | 2 | 67 | Permit issues | Ongoing
PRJ-005 | Kano Erosion Control Phase 2 | Erosion Control | Kano | BuildRight Nig Ltd | AECOM Nigeria | 2020 | 1557483000 | 2400288000 | 842805000 | 26 | 42 | 16 | 78 | Design changes | Ongoing
PRJ-006 | Rivers School Block Phase 3 | School Block | Rivers | Nile Construction | Julius Berger Consult | 2020 | 1356842000 | 1860355000 | 503513000 | 16 | 23 | 7 | 51 | Labour dispute | Ongoing
PRJ-007 | Rivers Housing Estate Phase 1 | Housing Estate | Rivers | Greenfield Eng Ltd | CCECC Consult | 2021 | 1979571000 | 2640747000 | 661176000 | 47 | 54 | 7 | 71 | Poor site supervision | Ongoing
PRJ-008 | Enugu Road Construction Phase 3 | Road Construction | Enugu | Grandeur Works | Julius Berger Consult | 2019 | 461417000 | 699391000 | 237974000 | 32 | 37 | 5 | 93 | Community protest | Ongoing
PRJ-009 | Rivers Culvert Phase 1 | Culvert | Rivers | Pioneer Builders Ltd | Mott McDonald | 2020 | 1502729000 | 1913555000 | 410826000 | 39 | 64 | 25 | 81 | Funding delay | Ongoing
PRJ-010 | Anambra Drainage System Phase 1 | Drainage System | Anambra | Greenfield Eng Ltd | AECOM Nigeria | 2019 | 1729151000 | 1801265000 | 72114000 | 22 | 34 | 12 | 84 | Permit issues | Ongoing
PRJ-011 | Delta Hospital Phase 2 | Hospital | Delta | Mainland Const. Co. | CCECC Consult | 2023 | 540258000 | 692576000 | 152318000 | 12 | 18 | 6 | 44 | Labour dispute | Delayed
PRJ-012 | Abuja School Block Phase 1 | School Block | Abuja | Pioneer Builders Ltd | CCECC Consult | 2020 | 934761000 | 1422977000 | 488216000 | 28 | 47 | 19 | 52 | Labour dispute | Ongoing
PRJ-013 | Anambra Water Treatment Plant Phase 1 | Water Treatment Plant | Anambra | Mainland Const. Co. | Mott McDonald | 2020 | 779132000 | 815696000 | 36564000 | 45 | 74 | 29 | 71 | Equipment breakdown | Ongoing
PRJ-014 | Enugu Bridge Phase 3 | Bridge | Enugu | Pioneer Builders Ltd | Mott McDonald | 2019 | 519700000 | 670628000 | 150928000 | 17 | 18 | 1 | 92 | Material price escalation | Ongoing
PRJ-015 | Rivers Drainage System Phase 3 | Drainage System | Rivers | Greenfield Eng Ltd | Scott Wilson | 2020 | 566860000 | 835245000 | 268385000 | 39 | 65 | 26 | 99 | Adverse weather | Ongoing
PRJ-016 | Delta Water Treatment Plant Phase 3 | Water Treatment Plant | Delta | Nile Construction | CCECC Consult | 2023 | 930398000 | 1022269000 | 91871000 | 16 | 20 | 4 | 100 | Adverse weather | Completed
PRJ-017 | Lagos Housing Estate Phase 3 | Housing Estate | Lagos | BuildRight Nig Ltd | AECOM Nigeria | 2020 | 181431000 | 175779000 | -5652000 | 33 | 35 | 2 | 60 | Design changes | Ongoing
PRJ-018 | Kano Culvert Phase 1 | Culvert | Kano | Horizon Builders | Mott McDonald | 2023 | 1173613000 | 1286043000 | 112430000 | 42 | 66 | 24 | 54 | Material price escalation | Ongoing
PRJ-019 | Enugu Hospital Phase 1 | Hospital | Enugu | Grandeur Works | CCECC Consult | 2022 | 1734482000 | 1704133000 | -30349000 | 18 | 19 | 1 | 73 | Material price escalation | Ongoing
PRJ-020 | Kano Housing Estate Phase 3 | Housing Estate | Kano | Horizon Builders | CCECC Consult | 2020 | 872669000 | 974882000 | 102213000 | 27 | 44 | 17 | 39 | Equipment breakdown | Delayed
PRJ-021 | Lagos Bridge Phase 2 | Bridge | Lagos | Horizon Builders | AECOM Nigeria | 2019 | 1856416000 | 2708915000 | 852499000 | 22 | 28 | 6 | 91 | Adverse weather | Ongoing
PRJ-022 | Rivers Road Construction Phase 1 | Road Construction | Rivers | Grandeur Works | AECOM Nigeria | 2022 | 567146000 | 805598000 | 238452000 | 41 | 49 | 8 | 92 | Contractor default | Ongoing
PRJ-023 | Kano Water Treatment Plant Phase 1 | Water Treatment Plant | Kano | Tetrazzini & Sons Ltd | Scott Wilson | 2023 | 168867000 | 192198000 | 23331000 | 15 | 21 | 6 | 94 | Labour dispute | Ongoing
PRJ-024 | Anambra Road Construction Phase 3 | Road Construction | Anambra | BuildRight Nig Ltd | Mott McDonald | 2019 | 1210318000 | 1640135000 | 429817000 | 27 | 35 | 8 | 61 | Permit issues | Ongoing
PRJ-025 | Edo Road Construction Phase 2 | Road Construction | Edo | BuildRight Nig Ltd | CCECC Consult | 2023 | 1152193000 | 1313295000 | 161102000 | 28 | 32 | 4 | 70 | Adverse weather | Ongoing
PRJ-026 | Rivers Hospital Phase 3 | Hospital | Rivers | Pioneer Builders Ltd | CCECC Consult | 2021 | 1861586000 | 2813677000 | 952091000 | 12 | 16 | 4 | 42 | Material price escalation | Delayed
PRJ-027 | Anambra Housing Estate Phase 3 | Housing Estate | Anambra | Pioneer Builders Ltd | Mott McDonald | 2021 | 1767685000 | 2611864000 | 844179000 | 35 | 42 | 7 | 86 | Labour dispute | Ongoing
PRJ-028 | Edo Water Treatment Plant Phase 1 | Water Treatment Plant | Edo | Horizon Builders | AECOM Nigeria | 2023 | 633789000 | 854369000 | 220580000 | 20 | 24 | 4 | 43 | Labour dispute | Delayed
PRJ-029 | Oyo Water Treatment Plant Phase 1 | Water Treatment Plant | Oyo | Mainland Const. Co. | Mott McDonald | 2021 | 447015000 | 594773000 | 147758000 | 28 | 38 | 10 | 62 | Poor site supervision | Ongoing
PRJ-030 | Oyo Hospital Phase 3 | Hospital | Oyo | Tetrazzini & Sons Ltd | AECOM Nigeria | 2021 | 1553682000 | 2069921000 | 516239000 | 28 | 31 | 3 | 86 | Labour dispute | Ongoing
PRJ-031 | Anambra Hospital Phase 3 | Hospital | Anambra | Tetrazzini & Sons Ltd | AECOM Nigeria | 2019 | 1892849000 | 2583004000 | 690155000 | 21 | 29 | 8 | 77 | Permit issues | Ongoing
PRJ-032 | Delta Drainage System Phase 3 | Drainage System | Delta | Fedex Const. Co. | AECOM Nigeria | 2021 | 761070000 | 1149104000 | 388034000 | 14 | 23 | 9 | 56 | Adverse weather | Ongoing
PRJ-033 | Enugu Bridge Phase 1 | Bridge | Enugu | Horizon Builders | CCECC Consult | 2023 | 1511481000 | 2275472000 | 763991000 | 27 | 43 | 16 | 52 | Community protest | Ongoing
PRJ-034 | Enugu Drainage System Phase 1 | Drainage System | Enugu | Grandeur Works | Mott McDonald | 2021 | 360436000 | 494074000 | 133638000 | 36 | 58 | 22 | 90 | Adverse weather | Ongoing
PRJ-035 | Enugu Culvert Phase 2 | Culvert | Enugu | Pioneer Builders Ltd | Mott McDonald | 2020 | 96146000 | 102480000 | 6334000 | 33 | 39 | 6 | 38 | Design changes | Delayed
PRJ-036 | Delta Retaining Wall Phase 1 | Retaining Wall | Delta | Horizon Builders | Julius Berger Consult | 2019 | 274916000 | 421237000 | 146321000 | 23 | 32 | 9 | 63 | Poor site supervision | Ongoing
PRJ-037 | Delta Erosion Control Phase 1 | Erosion Control | Delta | Nile Construction | Julius Berger Consult | 2022 | 1232107000 | 1548578000 | 316471000 | 36 | 59 | 23 | 54 | Design changes | Ongoing
PRJ-038 | Lagos Hospital Phase 3 | Hospital | Lagos | Horizon Builders | Scott Wilson | 2020 | 760232000 | 754138000 | -6094000 | 33 | 47 | 14 | 45 | Design changes | Delayed
PRJ-039 | Delta Water Treatment Plant Phase 3 | Water Treatment Plant | Delta | Nile Construction | CCECC Consult | 2021 | 1131104000 | 1204743000 | 73639000 | 36 | 53 | 17 | 52 | Permit issues | Ongoing
PRJ-040 | Delta Water Treatment Plant Phase 3 | Water Treatment Plant | Delta | Horizon Builders | AECOM Nigeria | 2021 | 609482000 | 736213000 | 126731000 | 32 | 42 | 10 | 86 | Adverse weather | Ongoing
PRJ-041 | Rivers Culvert Phase 1 | Culvert | Rivers | BuildRight Nig Ltd | Julius Berger Consult | 2023 | 1344515000 | 1776853000 | 432338000 | 17 | 27 | 10 | 60 | Design changes | Ongoing
PRJ-042 | Rivers Housing Estate Phase 2 | Housing Estate | Rivers | Tetrazzini & Sons Ltd | AECOM Nigeria | 2020 | 1968675000 | 2592281000 | 623606000 | 16 | 21 | 5 | 54 | Community protest | Ongoing
PRJ-043 | Kano Hospital Phase 2 | Hospital | Kano | Fedex Const. Co. | AECOM Nigeria | 2019 | 1567920000 | 1695399000 | 127479000 | 45 | 60 | 15 | 61 | Material price escalation | Ongoing
PRJ-044 | Kaduna Drainage System Phase 3 | Drainage System | Kaduna | Horizon Builders | Scott Wilson | 2023 | 668731000 | 938330000 | 269599000 | 40 | 57 | 17 | 94 | Community protest | Ongoing
PRJ-045 | Rivers Culvert Phase 3 | Culvert | Rivers | Greenfield Eng Ltd | CCECC Consult | 2021 | 1515965000 | 2204088000 | 688123000 | 29 | 45 | 16 | 96 | Equipment breakdown | Ongoing
PRJ-046 | Oyo Housing Estate Phase 2 | Housing Estate | Oyo | Greenfield Eng Ltd | AECOM Nigeria | 2021 | 507262000 | 584117000 | 76855000 | 46 | 49 | 3 | 49 | Adverse weather | Delayed
PRJ-047 | Kano Drainage System Phase 3 | Drainage System | Kano | BuildRight Nig Ltd | CCECC Consult | 2022 | 695219000 | 854810000 | 159591000 | 15 | 17 | 2 | 83 | Community protest | Ongoing
PRJ-048 | Edo Road Construction Phase 3 | Road Construction | Edo | Grandeur Works | CCECC Consult | 2019 | 1888346000 | 2132259000 | 243913000 | 36 | 58 | 22 | 83 | Labour dispute | Ongoing
PRJ-049 | Edo Retaining Wall Phase 2 | Retaining Wall | Edo | Apex Infra Ltd | CCECC Consult | 2020 | 582224000 | 722764000 | 140540000 | 36 | 44 | 8 | 81 | Contractor default | Ongoing
PRJ-050 | Edo Drainage System Phase 1 | Drainage System | Edo | Horizon Builders | AECOM Nigeria | 2022 | 1204191000 | 1623008000 | 418817000 | 17 | 25 | 8 | 47 | Equipment breakdown | Delayed
Total | 50 | [7 empty] | 15082331000 |  |  | 10.44 |  |  | 50

## Phase_Breakdown
Project_ID | Phase | Phase_Budget_NGN | Phase_Actual_NGN | Phase_Overrun_NGN | Phase_Overrun_Pct
PRJ-001 | Design | 25768000 | 23969000 | -1799000 | -7
PRJ-001 | Procurement | 38652000 | 43579000 | 4927000 | 12.7
PRJ-001 | Mobilisation | 16105000 | 16540000 | 435000 | 2.7
PRJ-001 | Construction | 193259000 | 211833000 | 18574000 | 9.6
PRJ-001 | Testing & Commissioning | 32210000 | 43701000 | 11491000 | 35.7
PRJ-001 | Handover | 16105000 | 18158000 | 2053000 | 12.7
PRJ-002 | Design | 8140000 | 10999000 | 2859000 | 35.1
PRJ-002 | Procurement | 12209000 | 17082000 | 4873000 | 39.9
PRJ-002 | Mobilisation | 5087000 | 5348000 | 261000 | 5.1
PRJ-002 | Construction | 61047000 | 57942000 | -3105000 | -5.1
PRJ-002 | Testing & Commissioning | 10174000 | 9275000 | -899000 | -8.8
PRJ-002 | Handover | 5087000 | 6225000 | 1138000 | 22.4
PRJ-003 | Design | 28255000 | 42381000 | 14126000 | 50
PRJ-003 | Procurement | 42382000 | 47043000 | 4661000 | 11
PRJ-003 | Mobilisation | 17659000 | 22782000 | 5123000 | 29
PRJ-003 | Construction | 211911000 | 290051000 | 78140000 | 36.9
PRJ-003 | Testing & Commissioning | 35318000 | 45597000 | 10279000 | 29.1
PRJ-003 | Handover | 17659000 | 23885000 | 6226000 | 35.3
PRJ-004 | Design | 87652000 | 128828000 | 41176000 | 47
PRJ-004 | Procurement | 131477000 | 134056000 | 2579000 | 2
PRJ-004 | Mobilisation | 54782000 | 49974000 | -4808000 | -8.8
PRJ-004 | Construction | 657387000 | 651753000 | -5634000 | -0.9
PRJ-004 | Testing & Commissioning | 109564000 | 106905000 | -2659000 | -2.4
PRJ-004 | Handover | 54782000 | 71308000 | 16526000 | 30.2
PRJ-005 | Design | 124599000 | 154301000 | 29702000 | 23.8
PRJ-005 | Procurement | 186898000 | 192650000 | 5752000 | 3.1
PRJ-005 | Mobilisation | 77874000 | 102769000 | 24895000 | 32
PRJ-005 | Construction | 934490000 | 1271036000 | 336546000 | 36
PRJ-005 | Testing & Commissioning | 155748000 | 155853000 | 105000 | 0.1
PRJ-005 | Handover | 77874000 | 98460000 | 20586000 | 26.4
PRJ-006 | Design | 108547000 | 146403000 | 37856000 | 34.9
PRJ-006 | Procurement | 162821000 | 157728000 | -5093000 | -3.1
PRJ-006 | Mobilisation | 67842000 | 94408000 | 26566000 | 39.2
PRJ-006 | Construction | 814105000 | 1203925000 | 389820000 | 47.9
PRJ-006 | Testing & Commissioning | 135684000 | 130916000 | -4768000 | -3.5
PRJ-006 | Handover | 67842000 | 62103000 | -5739000 | -8.5
PRJ-007 | Design | 158366000 | 172171000 | 13805000 | 8.7
PRJ-007 | Procurement | 237549000 | 310336000 | 72787000 | 30.6
PRJ-007 | Mobilisation | 98979000 | 145984000 | 47005000 | 47.5
PRJ-007 | Construction | 1187743000 | 1351643000 | 163900000 | 13.8
PRJ-007 | Testing & Commissioning | 197957000 | 263087000 | 65130000 | 32.9
PRJ-007 | Handover | 98979000 | 93594000 | -5385000 | -5.4
PRJ-008 | Design | 36913000 | 48517000 | 11604000 | 31.4
PRJ-008 | Procurement | 55370000 | 70671000 | 15301000 | 27.6
PRJ-008 | Mobilisation | 23071000 | 22174000 | -897000 | -3.9
PRJ-008 | Construction | 276850000 | 377482000 | 100632000 | 36.3
PRJ-008 | Testing & Commissioning | 46142000 | 65068000 | 18926000 | 41
PRJ-008 | Handover | 23071000 | 29075000 | 6004000 | 26
PRJ-009 | Design | 120218000 | 116928000 | -3290000 | -2.7
PRJ-009 | Procurement | 180327000 | 268743000 | 88416000 | 49
PRJ-009 | Mobilisation | 75136000 | 102905000 | 27769000 | 37
PRJ-009 | Construction | 901637000 | 999304000 | 97667000 | 10.8
PRJ-009 | Testing & Commissioning | 150273000 | 173870000 | 23597000 | 15.7
PRJ-009 | Handover | 75136000 | 84328000 | 9192000 | 12.2
PRJ-010 | Design | 138332000 | 166493000 | 28161000 | 20.4
PRJ-010 | Procurement | 207498000 | 229231000 | 21733000 | 10.5
PRJ-010 | Mobilisation | 86458000 | 121884000 | 35426000 | 41
PRJ-010 | Construction | 1037491000 | 1445638000 | 408147000 | 39.3
PRJ-010 | Testing & Commissioning | 172915000 | 166573000 | -6342000 | -3.7
PRJ-010 | Handover | 86458000 | 127653000 | 41195000 | 47.6
PRJ-011 | Design | 43221000 | 55381000 | 12160000 | 28.1
PRJ-011 | Procurement | 64831000 | 90583000 | 25752000 | 39.7
PRJ-011 | Mobilisation | 27013000 | 35776000 | 8763000 | 32.4
PRJ-011 | Construction | 324155000 | 376439000 | 52284000 | 16.1
PRJ-011 | Testing & Commissioning | 54026000 | 72410000 | 18384000 | 34
PRJ-011 | Handover | 27013000 | 39960000 | 12947000 | 47.9
PRJ-012 | Design | 74781000 | 79421000 | 4640000 | 6.2
PRJ-012 | Procurement | 112171000 | 155348000 | 43177000 | 38.5
PRJ-012 | Mobilisation | 46738000 | 57156000 | 10418000 | 22.3
PRJ-012 | Construction | 560857000 | 667475000 | 106618000 | 19
PRJ-012 | Testing & Commissioning | 93476000 | 108558000 | 15082000 | 16.1
PRJ-012 | Handover | 46738000 | 62564000 | 15826000 | 33.9
PRJ-013 | Design | 62331000 | 66136000 | 3805000 | 6.1
PRJ-013 | Procurement | 93496000 | 131925000 | 38429000 | 41.1
PRJ-013 | Mobilisation | 38957000 | 54479000 | 15522000 | 39.8
PRJ-013 | Construction | 467479000 | 445039000 | -22440000 | -4.8
PRJ-013 | Testing & Commissioning | 77913000 | 111336000 | 33423000 | 42.9
PRJ-013 | Handover | 38957000 | 40761000 | 1804000 | 4.6
PRJ-014 | Design | 41576000 | 49011000 | 7435000 | 17.9
PRJ-014 | Procurement | 62364000 | 78965000 | 16601000 | 26.6
PRJ-014 | Mobilisation | 25985000 | 29295000 | 3310000 | 12.7
PRJ-014 | Construction | 311820000 | 286008000 | -25812000 | -8.3
PRJ-014 | Testing & Commissioning | 51970000 | 73307000 | 21337000 | 41.1
PRJ-014 | Handover | 25985000 | 26222000 | 237000 | 0.9
PRJ-015 | Design | 45349000 | 46586000 | 1237000 | 2.7
PRJ-015 | Procurement | 68023000 | 93783000 | 25760000 | 37.9
PRJ-015 | Mobilisation | 28343000 | 31296000 | 2953000 | 10.4
PRJ-015 | Construction | 340116000 | 485751000 | 145635000 | 42.8
PRJ-015 | Testing & Commissioning | 56686000 | 74866000 | 18180000 | 32.1
PRJ-015 | Handover | 28343000 | 30207000 | 1864000 | 6.6
PRJ-016 | Design | 74432000 | 67442000 | -6990000 | -9.4
PRJ-016 | Procurement | 111648000 | 163993000 | 52345000 | 46.9
PRJ-016 | Mobilisation | 46520000 | 44258000 | -2262000 | -4.9
PRJ-016 | Construction | 558239000 | 743599000 | 185360000 | 33.2
PRJ-016 | Testing & Commissioning | 93040000 | 111010000 | 17970000 | 19.3
PRJ-016 | Handover | 46520000 | 63030000 | 16510000 | 35.5
PRJ-017 | Design | 14514000 | 19077000 | 4563000 | 31.4
PRJ-017 | Procurement | 21772000 | 28032000 | 6260000 | 28.8
PRJ-017 | Mobilisation | 9072000 | 10836000 | 1764000 | 19.4
PRJ-017 | Construction | 108859000 | 149764000 | 40905000 | 37.6
PRJ-017 | Testing & Commissioning | 18143000 | 17342000 | -801000 | -4.4
PRJ-017 | Handover | 9072000 | 9371000 | 299000 | 3.3
PRJ-018 | Design | 93889000 | 123471000 | 29582000 | 31.5
PRJ-018 | Procurement | 140834000 | 152625000 | 11791000 | 8.4
PRJ-018 | Mobilisation | 58681000 | 73289000 | 14608000 | 24.9
PRJ-018 | Construction | 704168000 | 833704000 | 129536000 | 18.4
PRJ-018 | Testing & Commissioning | 117361000 | 143011000 | 25650000 | 21.9
PRJ-018 | Handover | 58681000 | 67794000 | 9113000 | 15.5
PRJ-019 | Design | 138759000 | 186986000 | 48227000 | 34.8
PRJ-019 | Procurement | 208138000 | 228634000 | 20496000 | 9.8
PRJ-019 | Mobilisation | 86724000 | 114624000 | 27900000 | 32.2
PRJ-019 | Construction | 1040689000 | 1105784000 | 65095000 | 6.3
PRJ-019 | Testing & Commissioning | 173448000 | 182266000 | 8818000 | 5.1
PRJ-019 | Handover | 86724000 | 84330000 | -2394000 | -2.8
PRJ-020 | Design | 69814000 | 70900000 | 1086000 | 1.6
PRJ-020 | Procurement | 104720000 | 101760000 | -2960000 | -2.8
PRJ-020 | Mobilisation | 43633000 | 53299000 | 9666000 | 22.2
PRJ-020 | Construction | 523601000 | 710691000 | 187090000 | 35.7
PRJ-020 | Testing & Commissioning | 87267000 | 88235000 | 968000 | 1.1
PRJ-020 | Handover | 43633000 | 44935000 | 1302000 | 3
PRJ-021 | Design | 148513000 | 176808000 | 28295000 | 19.1
PRJ-021 | Procurement | 222770000 | 297342000 | 74572000 | 33.5
PRJ-021 | Mobilisation | 92821000 | 137929000 | 45108000 | 48.6
PRJ-021 | Construction | 1113850000 | 1353085000 | 239235000 | 21.5
PRJ-021 | Testing & Commissioning | 185642000 | 198600000 | 12958000 | 7
PRJ-021 | Handover | 92821000 | 89137000 | -3684000 | -4
PRJ-022 | Design | 45372000 | 46119000 | 747000 | 1.6
PRJ-022 | Procurement | 68058000 | 70541000 | 2483000 | 3.6
PRJ-022 | Mobilisation | 28357000 | 28574000 | 217000 | 0.8
PRJ-022 | Construction | 340288000 | 309148000 | -31140000 | -9.2
PRJ-022 | Testing & Commissioning | 56715000 | 69220000 | 12505000 | 22
PRJ-022 | Handover | 28357000 | 30188000 | 1831000 | 6.5
PRJ-023 | Design | 13509000 | 20055000 | 6546000 | 48.5
PRJ-023 | Procurement | 20264000 | 24966000 | 4702000 | 23.2
PRJ-023 | Mobilisation | 8443000 | 11132000 | 2689000 | 31.8
PRJ-023 | Construction | 101320000 | 98865000 | -2455000 | -2.4
PRJ-023 | Testing & Commissioning | 16887000 | 23998000 | 7111000 | 42.1
PRJ-023 | Handover | 8443000 | 10085000 | 1642000 | 19.5
PRJ-024 | Design | 96825000 | 137843000 | 41018000 | 42.4
PRJ-024 | Procurement | 145238000 | 180740000 | 35502000 | 24.4
PRJ-024 | Mobilisation | 60516000 | 71508000 | 10992000 | 18.2
PRJ-024 | Construction | 726191000 | 845491000 | 119300000 | 16.4
PRJ-024 | Testing & Commissioning | 121032000 | 122317000 | 1285000 | 1.1
PRJ-024 | Handover | 60516000 | 56330000 | -4186000 | -6.9
PRJ-025 | Design | 92175000 | 135003000 | 42828000 | 46.5
PRJ-025 | Procurement | 138263000 | 164068000 | 25805000 | 18.7
PRJ-025 | Mobilisation | 57610000 | 80266000 | 22656000 | 39.3
PRJ-025 | Construction | 691316000 | 788394000 | 97078000 | 14
PRJ-025 | Testing & Commissioning | 115219000 | 108819000 | -6400000 | -5.6
PRJ-025 | Handover | 57610000 | 73606000 | 15996000 | 27.8
PRJ-026 | Design | 148927000 | 138825000 | -10102000 | -6.8
PRJ-026 | Procurement | 223390000 | 221049000 | -2341000 | -1
PRJ-026 | Mobilisation | 93079000 | 115204000 | 22125000 | 23.8
PRJ-026 | Construction | 1116952000 | 1208879000 | 91927000 | 8.2
PRJ-026 | Testing & Commissioning | 186159000 | 278559000 | 92400000 | 49.6
PRJ-026 | Handover | 93079000 | 90386000 | -2693000 | -2.9
PRJ-027 | Design | 141415000 | 192136000 | 50721000 | 35.9
PRJ-027 | Procurement | 212122000 | 268078000 | 55956000 | 26.4
PRJ-027 | Mobilisation | 88384000 | 121479000 | 33095000 | 37.4
PRJ-027 | Construction | 1060611000 | 1098170000 | 37559000 | 3.5
PRJ-027 | Testing & Commissioning | 176768000 | 214516000 | 37748000 | 21.4
PRJ-027 | Handover | 88384000 | 103437000 | 15053000 | 17
PRJ-028 | Design | 50703000 | 59101000 | 8398000 | 16.6
PRJ-028 | Procurement | 76055000 | 107701000 | 31646000 | 41.6
PRJ-028 | Mobilisation | 31689000 | 47344000 | 15655000 | 49.4
PRJ-028 | Construction | 380273000 | 411922000 | 31649000 | 8.3
PRJ-028 | Testing & Commissioning | 63379000 | 80657000 | 17278000 | 27.3
PRJ-028 | Handover | 31689000 | 40111000 | 8422000 | 26.6
PRJ-029 | Design | 35761000 | 48065000 | 12304000 | 34.4
PRJ-029 | Procurement | 53642000 | 78776000 | 25134000 | 46.9
PRJ-029 | Mobilisation | 22351000 | 22902000 | 551000 | 2.5
PRJ-029 | Construction | 268209000 | 275347000 | 7138000 | 2.7
PRJ-029 | Testing & Commissioning | 44702000 | 57945000 | 13243000 | 29.6
PRJ-029 | Handover | 22351000 | 22222000 | -129000 | -0.6
PRJ-030 | Design | 124295000 | 124828000 | 533000 | 0.4
PRJ-030 | Procurement | 186442000 | 176195000 | -10247000 | -5.5
PRJ-030 | Mobilisation | 77684000 | 70040000 | -7644000 | -9.8
PRJ-030 | Construction | 932209000 | 1090966000 | 158757000 | 17
PRJ-030 | Testing & Commissioning | 155368000 | 195187000 | 39819000 | 25.6
PRJ-030 | Handover | 77684000 | 83491000 | 5807000 | 7.5
PRJ-031 | Design | 151428000 | 157316000 | 5888000 | 3.9
PRJ-031 | Procurement | 227142000 | 300775000 | 73633000 | 32.4
PRJ-031 | Mobilisation | 94642000 | 125097000 | 30455000 | 32.2
PRJ-031 | Construction | 1135709000 | 1331527000 | 195818000 | 17.2
PRJ-031 | Testing & Commissioning | 189285000 | 248423000 | 59138000 | 31.2
PRJ-031 | Handover | 94642000 | 137642000 | 43000000 | 45.4
PRJ-032 | Design | 60886000 | 83578000 | 22692000 | 37.3
PRJ-032 | Procurement | 91328000 | 116446000 | 25118000 | 27.5
PRJ-032 | Mobilisation | 38054000 | 49345000 | 11291000 | 29.7
PRJ-032 | Construction | 456642000 | 666789000 | 210147000 | 46
PRJ-032 | Testing & Commissioning | 76107000 | 87910000 | 11803000 | 15.5
PRJ-032 | Handover | 38054000 | 46682000 | 8628000 | 22.7
PRJ-033 | Design | 120918000 | 155813000 | 34895000 | 28.9
PRJ-033 | Procurement | 181378000 | 262100000 | 80722000 | 44.5
PRJ-033 | Mobilisation | 75574000 | 105500000 | 29926000 | 39.6
PRJ-033 | Construction | 906889000 | 855057000 | -51832000 | -5.7
PRJ-033 | Testing & Commissioning | 151148000 | 151081000 | -67000 | 0
PRJ-033 | Handover | 75574000 | 81965000 | 6391000 | 8.5
PRJ-034 | Design | 28835000 | 38909000 | 10074000 | 34.9
PRJ-034 | Procurement | 43252000 | 53698000 | 10446000 | 24.2
PRJ-034 | Mobilisation | 18022000 | 19341000 | 1319000 | 7.3
PRJ-034 | Construction | 216262000 | 210772000 | -5490000 | -2.5
PRJ-034 | Testing & Commissioning | 36044000 | 47333000 | 11289000 | 31.3
PRJ-034 | Handover | 18022000 | 23786000 | 5764000 | 32
PRJ-035 | Design | 7692000 | 11273000 | 3581000 | 46.6
PRJ-035 | Procurement | 11538000 | 13849000 | 2311000 | 20
PRJ-035 | Mobilisation | 4807000 | 5751000 | 944000 | 19.6
PRJ-035 | Construction | 57688000 | 54704000 | -2984000 | -5.2
PRJ-035 | Testing & Commissioning | 9615000 | 8883000 | -732000 | -7.6
PRJ-035 | Handover | 4807000 | 5572000 | 765000 | 15.9
PRJ-036 | Design | 21993000 | 24047000 | 2054000 | 9.3
PRJ-036 | Procurement | 32990000 | 34647000 | 1657000 | 5
PRJ-036 | Mobilisation | 13746000 | 13125000 | -621000 | -4.5
PRJ-036 | Construction | 164950000 | 243655000 | 78705000 | 47.7
PRJ-036 | Testing & Commissioning | 27492000 | 38532000 | 11040000 | 40.2
PRJ-036 | Handover | 13746000 | 17115000 | 3369000 | 24.5
PRJ-037 | Design | 98569000 | 144943000 | 46374000 | 47
PRJ-037 | Procurement | 147853000 | 221742000 | 73889000 | 50
PRJ-037 | Mobilisation | 61605000 | 80294000 | 18689000 | 30.3
PRJ-037 | Construction | 739264000 | 784881000 | 45617000 | 6.2
PRJ-037 | Testing & Commissioning | 123211000 | 113864000 | -9347000 | -7.6
PRJ-037 | Handover | 61605000 | 83398000 | 21793000 | 35.4
PRJ-038 | Design | 60819000 | 71906000 | 11087000 | 18.2
PRJ-038 | Procurement | 91228000 | 117767000 | 26539000 | 29.1
PRJ-038 | Mobilisation | 38012000 | 55104000 | 17092000 | 45
PRJ-038 | Construction | 456139000 | 460196000 | 4057000 | 0.9
PRJ-038 | Testing & Commissioning | 76023000 | 95120000 | 19097000 | 25.1
PRJ-038 | Handover | 38012000 | 48688000 | 10676000 | 28.1
PRJ-039 | Design | 90488000 | 108136000 | 17648000 | 19.5
PRJ-039 | Procurement | 135732000 | 129590000 | -6142000 | -4.5
PRJ-039 | Mobilisation | 56555000 | 62707000 | 6152000 | 10.9
PRJ-039 | Construction | 678662000 | 746518000 | 67856000 | 10
PRJ-039 | Testing & Commissioning | 113110000 | 147278000 | 34168000 | 30.2
PRJ-039 | Handover | 56555000 | 80005000 | 23450000 | 41.5
PRJ-040 | Design | 48759000 | 53532000 | 4773000 | 9.8
PRJ-040 | Procurement | 73138000 | 96265000 | 23127000 | 31.6
PRJ-040 | Mobilisation | 30474000 | 32696000 | 2222000 | 7.3
PRJ-040 | Construction | 365689000 | 536508000 | 170819000 | 46.7
PRJ-040 | Testing & Commissioning | 60948000 | 84604000 | 23656000 | 38.8
PRJ-040 | Handover | 30474000 | 37485000 | 7011000 | 23
PRJ-041 | Design | 107561000 | 126158000 | 18597000 | 17.3
PRJ-041 | Procurement | 161342000 | 175655000 | 14313000 | 8.9
PRJ-041 | Mobilisation | 67226000 | 73543000 | 6317000 | 9.4
PRJ-041 | Construction | 806709000 | 1195632000 | 388923000 | 48.2
PRJ-041 | Testing & Commissioning | 134452000 | 153612000 | 19160000 | 14.3
PRJ-041 | Handover | 67226000 | 81260000 | 14034000 | 20.9
PRJ-042 | Design | 157494000 | 235118000 | 77624000 | 49.3
PRJ-042 | Procurement | 236241000 | 305837000 | 69596000 | 29.5
PRJ-042 | Mobilisation | 98434000 | 120636000 | 22202000 | 22.6
PRJ-042 | Construction | 1181205000 | 1355963000 | 174758000 | 14.8
PRJ-042 | Testing & Commissioning | 196868000 | 199339000 | 2471000 | 1.3
PRJ-042 | Handover | 98434000 | 109957000 | 11523000 | 11.7
PRJ-043 | Design | 125434000 | 169821000 | 44387000 | 35.4
PRJ-043 | Procurement | 188150000 | 239937000 | 51787000 | 27.5
PRJ-043 | Mobilisation | 78396000 | 106305000 | 27909000 | 35.6
PRJ-043 | Construction | 940752000 | 961575000 | 20823000 | 2.2
PRJ-043 | Testing & Commissioning | 156792000 | 192781000 | 35989000 | 23
PRJ-043 | Handover | 78396000 | 114192000 | 35796000 | 45.7
PRJ-044 | Design | 53498000 | 62211000 | 8713000 | 16.3
PRJ-044 | Procurement | 80248000 | 105843000 | 25595000 | 31.9
PRJ-044 | Mobilisation | 33437000 | 32529000 | -908000 | -2.7
PRJ-044 | Construction | 401239000 | 595394000 | 194155000 | 48.4
PRJ-044 | Testing & Commissioning | 66873000 | 84616000 | 17743000 | 26.5
PRJ-044 | Handover | 33437000 | 34894000 | 1457000 | 4.4
PRJ-045 | Design | 121277000 | 120674000 | -603000 | -0.5
PRJ-045 | Procurement | 181916000 | 223848000 | 41932000 | 23.1
PRJ-045 | Mobilisation | 75798000 | 93334000 | 17536000 | 23.1
PRJ-045 | Construction | 909579000 | 869490000 | -40089000 | -4.4
PRJ-045 | Testing & Commissioning | 151596000 | 226690000 | 75094000 | 49.5
PRJ-045 | Handover | 75798000 | 109737000 | 33939000 | 44.8
PRJ-046 | Design | 40581000 | 47759000 | 7178000 | 17.7
PRJ-046 | Procurement | 60871000 | 59074000 | -1797000 | -3
PRJ-046 | Mobilisation | 25363000 | 35490000 | 10127000 | 39.9
PRJ-046 | Construction | 304357000 | 364932000 | 60575000 | 19.9
PRJ-046 | Testing & Commissioning | 50726000 | 67464000 | 16738000 | 33
PRJ-046 | Handover | 25363000 | 30571000 | 5208000 | 20.5
PRJ-047 | Design | 55618000 | 59181000 | 3563000 | 6.4
PRJ-047 | Procurement | 83426000 | 116866000 | 33440000 | 40.1
PRJ-047 | Mobilisation | 34761000 | 51729000 | 16968000 | 48.8
PRJ-047 | Construction | 417131000 | 436419000 | 19288000 | 4.6
PRJ-047 | Testing & Commissioning | 69522000 | 85565000 | 16043000 | 23.1
PRJ-047 | Handover | 34761000 | 39285000 | 4524000 | 13
PRJ-048 | Design | 151068000 | 219520000 | 68452000 | 45.3
PRJ-048 | Procurement | 226602000 | 273043000 | 46441000 | 20.5
PRJ-048 | Mobilisation | 94417000 | 134789000 | 40372000 | 42.8
PRJ-048 | Construction | 1133008000 | 1607077000 | 474069000 | 41.8
PRJ-048 | Testing & Commissioning | 188835000 | 201251000 | 12416000 | 6.6
PRJ-048 | Handover | 94417000 | 129729000 | 35312000 | 37.4
PRJ-049 | Design | 46578000 | 53517000 | 6939000 | 14.9
PRJ-049 | Procurement | 69867000 | 102044000 | 32177000 | 46.1
PRJ-049 | Mobilisation | 29111000 | 35068000 | 5957000 | 20.5
PRJ-049 | Construction | 349334000 | 486388000 | 137054000 | 39.2
PRJ-049 | Testing & Commissioning | 58222000 | 62280000 | 4058000 | 7
PRJ-049 | Handover | 29111000 | 31415000 | 2304000 | 7.9
PRJ-050 | Design | 96335000 | 120627000 | 24292000 | 25.2
PRJ-050 | Procurement | 144503000 | 216659000 | 72156000 | 49.9
PRJ-050 | Mobilisation | 60210000 | 71878000 | 11668000 | 19.4
PRJ-050 | Construction | 722515000 | 714681000 | -7834000 | -1.1
PRJ-050 | Testing & Commissioning | 120419000 | 147290000 | 26871000 | 22.3
PRJ-050 | Handover | 60210000 | 66657000 | 6447000 | 10.7

## Contractor_Scorecard
Contractor | Projects_Handled | Total_Budget_NGN | Total_Actual_NGN | Avg_Cost_Overrun_Pct | Avg_Planned_Duration | Avg_Actual_Duration | Delay_Rate_Pct | Performance_Score
Pioneer Builders Ltd | 8 | 8100351000 | 11541559000 | 42.5 | 30.8 | 39.1 | 100 | 0
Apex Infra Ltd | 2 | 683969000 | 831560000 | 21.6 | 41 | 52 | 100 | 0
Grandeur Works | 6 | 5365012000 | 6373825000 | 18.8 | 32.7 | 42.7 | 100 | 0
BuildRight Nig Ltd | 6 | 6141159000 | 8161160000 | 32.9 | 24.3 | 31.3 | 100 | 0
Nile Construction | 4 | 4650451000 | 5635945000 | 21.2 | 26 | 38.8 | 100 | 0
Greenfield Eng Ltd | 5 | 6298809000 | 8065462000 | 28 | 36.6 | 49.4 | 100 | 0
Mainland Const. Co. | 3 | 1766405000 | 2103045000 | 19.1 | 28.3 | 43.3 | 100 | 0
Horizon Builders | 10 | 9565520000 | 12572607000 | 31.4 | 28.3 | 40.8 | 100 | 0
Tetrazzini & Sons Ltd | 4 | 5584073000 | 7437404000 | 33.2 | 20 | 25.5 | 100 | 0
Fedex Const. Co. | 2 | 2328990000 | 2844503000 | 22.1 | 29.5 | 41.5 | 100 | 0

## Data_Dictionary
Table | Column | Data Type | Description
▶ Projects
| Project_ID | TEXT | Unique identifier for each project (e.g. PRJ-001)
| Project_Name | TEXT | Descriptive name: State + Type + Phase
| Project_Type | TEXT | Category of infrastructure project
| State | TEXT | Nigerian state where project is located
| Contractor | TEXT | Name of the main contractor
| Consultant | TEXT | Supervising consultant firm
| Year_Start | INTEGER | Year the project commenced
| Budget_NGN | CURRENCY | Original approved project budget (Naira)
| Actual_Cost_NGN | CURRENCY | Final or current actual expenditure (Naira)
| Cost_Overrun_NGN | CURRENCY | Actual Cost minus Budget (positive = overrun)
| Planned_Duration_Months | INTEGER | Original planned project duration in months
| Actual_Duration_Months | INTEGER | Actual or projected completion duration
| Schedule_Delay_Months | INTEGER | Actual minus Planned duration (positive = delay)
| Pct_Complete | INTEGER | Percentage of work completed (0–100)
| Primary_Delay_Reason | TEXT | Main recorded reason for schedule delay
| Status | TEXT | Project status: Completed / Ongoing / Delayed
▶ Phase_Breakdown
| Project_ID | TEXT | Foreign key linking to Projects table
| Phase | TEXT | Project phase name (Design, Procurement, etc.)
| Phase_Budget_NGN | CURRENCY | Allocated budget for this phase
| Phase_Actual_NGN | CURRENCY | Actual spend for this phase
| Phase_Overrun_NGN | CURRENCY | Phase overrun in Naira
| Phase_Overrun_Pct | DECIMAL | Phase overrun as percentage of phase budget
▶ Contractor_Scorecard
| Contractor | TEXT | Contractor name (primary key)
| Projects_Handled | INTEGER | Total number of projects awarded
| Total_Budget_NGN | CURRENCY | Sum of all project budgets
| Total_Actual_NGN | CURRENCY | Sum of all actual costs
| Avg_Cost_Overrun_Pct | DECIMAL | Average cost overrun % across all projects
| Avg_Planned_Duration | DECIMAL | Average planned project duration in months
| Avg_Actual_Duration | DECIMAL | Average actual project duration in months
| Delay_Rate_Pct | DECIMAL | % of projects with schedule delays
| Performance_Score | DECIMAL | Composite score: 100 minus overrun & delay rates

## README
🏗️ CONSTRUCTION PROJECT ANALYTICS DATASET
Project Overview
Purpose | Realistic dataset simulating a Nigerian construction PMO with 50 projects across 10 states — designed to support end-to-end data analysis.
Analyst | MONSURU ADELEKE
Date Created | 2026
Tool Used | Microsoft Excel + SQL
Sheet Guide
1. Projects | Master table — 50 projects with budget, cost, schedule & status data
2. Phase_Breakdown | Per-phase cost breakdown for every project (6 phases × 50 projects)
3. Contractor_Scorecard | Aggregated contractor performance metrics
4. Data_Dictionary | Column definitions & data types for all three tables