## README
🏗️ CONSTRUCTION PROJECT ANALYTICS DATASET
Project Overview
Purpose | Realistic dataset simulating a Nigerian construction PMO with 50 projects across 10 states — designed to support end-to-end data analysis.
Analyst | [Your Name]
Date Created | 2024
Tool Used | Microsoft Excel + SQL
Sheet Guide
1. Projects | Master table — 50 projects with budget, cost, schedule & status data
2. Phase_Breakdown | Per-phase cost breakdown for every project (6 phases × 50 projects)
3. Contractor_Scorecard | Aggregated contractor performance metrics
4. Data_Dictionary | Column definitions & data types for all three tables

## Projects
Project_ID | Project_Name | Project_Type | State | Contractor | Consultant | Year_Start | Budget_NGN | Actual_Cost_NGN | Cost_Overrun_NGN | Planned_Duration_Months | Actual_Duration_Months | Schedule_Delay_Months | Pct_Complete | Primary_Delay_Reason | Status
PRJ-001 | Lagos Bridge Phase 1 | Bridge | Lagos | Pioneer Builders Ltd | Mott McDonald | 2020 | 322099000 | 325802000 | 3703000 | 46 | 49 | 3 | 84 | Poor site supervision | Ongoing
PRJ-002 | Kano Bridge Phase 2 | Bridge | Kano | Apex Infra Ltd | Scott Wilson | 2023 | 101745000 | 108796000 | 7051000 | 46 | 60 | 14 | 87 | Permit issues | Ongoing
PRJ-003 | Rivers Road Construction Phase 2 | Road Construction | Rivers | Grandeur Works | Julius Berger Consult | 2021 | 353185000 | 538370000 | 185185000 | 33 | 35 | 2 | 78 | Material price escalation | Ongoing
PRJ-004 | Edo School Block Phase 2 | School Block | Edo | Pioneer Builders Ltd | AECOM Nigeria | 2022 | 1095645000 | 1680576000 | 584931000 | 36 | 38 | 2 | 67 | Permit issues | Ongoing
PRJ-005 | Kano Erosion Control Phase 2 | Erosion Control | Kano | BuildRight Nig Ltd | AECOM Nigeria | 2020 | 1557483000 | 2400288000 | 842805000 | 26 | 42 | 16 | 78 | Design changes | Ongoing
PRJ-006 | Rivers School Block Phase 3 | School Block | Rivers | Nile Construction | Julius Berger Consult | 2020 | 1356842000 | 1860355000 | 503513000 | 16 | 23 | 7 | 51 | Labour dispute | Ongoing
PRJ-007 | Rivers Housing Estate Phase 1 | Housing Estate | Rivers | Greenfield Eng Ltd | CCECC Consult | 2021 | 1979571000 | 2640747000 | 661176000 | 47 | 54 | 7 | 71 | Poor site supervision | Ongoing
PRJ-008 | Enugu Road Construction Phase 3 | Road Construction | Enugu | Grandeur Works | Julius Berger Consult | 2019 | 461417000 | 699391000 | 237974000 | 32 | 37 | 5 | 93 | Community protest | Ongoing
PRJ-009 | Rivers Culvert Phase 1 | Culvert | Rivers | Pioneer Builders Ltd | Mott McDonald | 2020 | 1502729000 | 1913555000 | 410826000 | 39 | 64 | 25 | 81 | Funding delay | Ongoing
PRJ-010 | Anambra Drainage System Phase 1 | Drainage System | Anambra | Greenfield Eng Ltd | AECOM Nigeria | 2019 | 1729151000 | 1801265000 | 72114000 | 22 | 34 | 12 | 84 | Permit issues | Ongoing
PRJ-011 | Delta Hospital Phase 2 | Hospital | Delta | Mainland Const. Co. | CCECC Consult | 2023 | 540258000 | 692576000 | 152318000 | 12 | 18 | 6 | 44 | Labour dispute | Delayed
PRJ-012 | Abuja School Block Phase 1 | School Block | Abuja | Pioneer Builders Ltd | CCECC Consult | 2020 | 934761000 | 1422977000 | 488216000 | 28 | 47 | 19 | 52 | Labour dispute | Ongoing
PRJ-013 | Anambra Water Treatment Plant Phase 1 | Water Treatment Plant | Anambra | Mainland Const. Co. | Mott McDonald | 2020 | 779132000 | 815696000 | 36564000 | 45 | 74 | 29 | 71 | Equipment breakdown | Ongoing
PRJ-014 | Enugu Bridge Phase 3 | Bridge | Enugu | Pioneer Builders Ltd | Mott McDonald | 2019 | 519700000 | 670628000 | 150928000 | 17 | 18 | 1 | 92 | Material price escalation | Ongoing
PRJ-015 | Rivers Drainage System Phase 3 | Drainage System | Rivers | Greenfield Eng Ltd | Scott Wilson | 2020 | 566860000 | 835245000 | 268385000 | 39 | 65 | 26 | 99 | Adverse weather | Ongoing
PRJ-016 | Delta Water Treatment Plant Phase 3 | Water Treatment Plant | Delta | Nile Construction | CCECC Consult | 2023 | 930398000 | 1022269000 | 91871000 | 16 | 20 | 4 | 100 | Adverse weather | Completed
PRJ-017 | Lagos Housing Estate Phase 3 | Housing Estate | Lagos | BuildRight Nig Ltd | AECOM Nigeria | 2020 | 181431000 | 175779000 | -5652000 | 33 | 35 | 2 | 60 | Design changes | Ongoing
PRJ-018 | Kano Culvert Phase 1 | Culvert | Kano | Horizon Builders | Mott McDonald | 2023 | 1173613000 | 1286043000 | 112430000 | 42 | 66 | 24 | 54 | Material price escalation | Ongoing
PRJ-019 | Enugu Hospital Phase 1 | Hospital | Enugu | Grandeur Works | CCECC Consult | 2022 | 1734482000 | 1704133000 | -30349000 | 18 | 19 | 1 | 73 | Material price escalation | Ongoing
PRJ-020 | Kano Housing Estate Phase 3 | Housing Estate | Kano | Horizon Builders | CCECC Consult | 2020 | 872669000 | 974882000 | 102213000 | 27 | 44 | 17 | 39 | Equipment breakdown | Delayed
PRJ-021 | Lagos Bridge Phase 2 | Bridge | Lagos | Horizon Builders | AECOM Nigeria | 2019 | 1856416000 | 2708915000 | 852499000 | 22 | 28 | 6 | 91 | Adverse weather | Ongoing
PRJ-022 | Rivers Road Construction Phase 1 | Road Construction | Rivers | Grandeur Works | AECOM Nigeria | 2022 | 567146000 | 805598000 | 238452000 | 41 | 49 | 8 | 92 | Contractor default | Ongoing
PRJ-023 | Kano Water Treatment Plant Phase 1 | Water Treatment Plant | Kano | Tetrazzini & Sons Ltd | Scott Wilson | 2023 | 168867000 | 192198000 | 23331000 | 15 | 21 | 6 | 94 | Labour dispute | Ongoing
PRJ-024 | Anambra Road Construction Phase 3 | Road Construction | Anambra | BuildRight Nig Ltd | Mott McDonald | 2019 | 1210318000 | 1640135000 | 429817000 | 27 | 35 | 8 | 61 | Permit issues | Ongoing
PRJ-025 | Edo Road Construction Phase 2 | Road Construction | Edo | BuildRight Nig Ltd | CCECC Consult | 2023 | 1152193000 | 1313295000 | 161102000 | 28 | 32 | 4 | 70 | Adverse weather | Ongoing
PRJ-026 | Rivers Hospital Phase 3 | Hospital | Rivers | Pioneer Builders Ltd | CCECC Consult | 2021 | 1861586000 | 2813677000 | 952091000 | 12 | 16 | 4 | 42 | Material price escalation | Delayed
PRJ-027 | Anambra Housing Estate Phase 3 | Housing Estate | Anambra | Pioneer Builders Ltd | Mott McDonald | 2021 | 1767685000 | 2611864000 | 844179000 | 35 | 42 | 7 | 86 | Labour dispute | Ongoing
PRJ-028 | Edo Water Treatment Plant Phase 1 | Water Treatment Plant | Edo | Horizon Builders | AECOM Nigeria | 2023 | 633789000 | 854369000 | 220580000 | 20 | 24 | 4 | 43 | Labour dispute | Delayed
PRJ-029 | Oyo Water Treatment Plant Phase 1 | Water Treatment Plant | Oyo | Mainland Const. Co. | Mott McDonald | 2021 | 447015000 | 594773000 | 147758000 | 28 | 38 | 10 | 62 | Poor site supervision | Ongoing
PRJ-030 | Oyo Hospital Phase 3 | Hospital | Oyo | Tetrazzini & Sons Ltd | AECOM Nigeria | 2021 | 1553682000 | 2069921000 | 516239000 | 28 | 31 | 3 | 86 | Labour dispute | Ongoing
PRJ-031 | Anambra Hospital Phase 3 | Hospital | Anambra | Tetrazzini & Sons Ltd | AECOM Nigeria | 2019 | 1892849000 | 2583004000 | 690155000 | 21 | 29 | 8 | 77 | Permit issues | Ongoing
PRJ-032 | Delta Drainage System Phase 3 | Drainage System | Delta | Fedex Const. Co. | AECOM Nigeria | 2021 | 761070000 | 1149104000 | 388034000 | 14 | 23 | 9 | 56 | Adverse weather | Ongoing
PRJ-033 | Enugu Bridge Phase 1 | Bridge | Enugu | Horizon Builders | CCECC Consult | 2023 | 1511481000 | 2275472000 | 763991000 | 27 | 43 | 16 | 52 | Community protest | Ongoing
PRJ-034 | Enugu Drainage System Phase 1 | Drainage System | Enugu | Grandeur Works | Mott McDonald | 2021 | 360436000 | 494074000 | 133638000 | 36 | 58 | 22 | 90 | Adverse weather | Ongoing
PRJ-035 | Enugu Culvert Phase 2 | Culvert | Enugu | Pioneer Builders Ltd | Mott McDonald | 2020 | 96146000 | 102480000 | 6334000 | 33 | 39 | 6 | 38 | Design changes | Delayed
PRJ-036 | Delta Retaining Wall Phase 1 | Retaining Wall | Delta | Horizon Builders | Julius Berger Consult | 2019 | 274916000 | 421237000 | 146321000 | 23 | 32 | 9 | 63 | Poor site supervision | Ongoing
PRJ-037 | Delta Erosion Control Phase 1 | Erosion Control | Delta | Nile Construction | Julius Berger Consult | 2022 | 1232107000 | 1548578000 | 316471000 | 36 | 59 | 23 | 54 | Design changes | Ongoing
PRJ-038 | Lagos Hospital Phase 3 | Hospital | Lagos | Horizon Builders | Scott Wilson | 2020 | 760232000 | 754138000 | -6094000 | 33 | 47 | 14 | 45 | Design changes | Delayed
PRJ-039 | Delta Water Treatment Plant Phase 3 | Water Treatment Plant | Delta | Nile Construction | CCECC Consult | 2021 | 1131104000 | 1204743000 | 73639000 | 36 | 53 | 17 | 52 | Permit issues | Ongoing
PRJ-040 | Delta Water Treatment Plant Phase 3 | Water Treatment Plant | Delta | Horizon Builders | AECOM Nigeria | 2021 | 609482000 | 736213000 | 126731000 | 32 | 42 | 10 | 86 | Adverse weather | Ongoing
PRJ-041 | Rivers Culvert Phase 1 | Culvert | Rivers | BuildRight Nig Ltd | Julius Berger Consult | 2023 | 1344515000 | 1776853000 | 432338000 | 17 | 27 | 10 | 60 | Design changes | Ongoing
PRJ-042 | Rivers Housing Estate Phase 2 | Housing Estate | Rivers | Tetrazzini & Sons Ltd | AECOM Nigeria | 2020 | 1968675000 | 2592281000 | 623606000 | 16 | 21 | 5 | 54 | Community protest | Ongoing
PRJ-043 | Kano Hospital Phase 2 | Hospital | Kano | Fedex Const. Co. | AECOM Nigeria | 2019 | 1567920000 | 1695399000 | 127479000 | 45 | 60 | 15 | 61 | Material price escalation | Ongoing
PRJ-044 | Kaduna Drainage System Phase 3 | Drainage System | Kaduna | Horizon Builders | Scott Wilson | 2023 | 668731000 | 938330000 | 269599000 | 40 | 57 | 17 | 94 | Community protest | Ongoing
PRJ-045 | Rivers Culvert Phase 3 | Culvert | Rivers | Greenfield Eng Ltd | CCECC Consult | 2021 | 1515965000 | 2204088000 | 688123000 | 29 | 45 | 16 | 96 | Equipment breakdown | Ongoing
PRJ-046 | Oyo Housing Estate Phase 2 | Housing Estate | Oyo | Greenfield Eng Ltd | AECOM Nigeria | 2021 | 507262000 | 584117000 | 76855000 | 46 | 49 | 3 | 49 | Adverse weather | Delayed
PRJ-047 | Kano Drainage System Phase 3 | Drainage System | Kano | BuildRight Nig Ltd | CCECC Consult | 2022 | 695219000 | 854810000 | 159591000 | 15 | 17 | 2 | 83 | Community protest | Ongoing
PRJ-048 | Edo Road Construction Phase 3 | Road Construction | Edo | Grandeur Works | CCECC Consult | 2019 | 1888346000 | 2132259000 | 243913000 | 36 | 58 | 22 | 83 | Labour dispute | Ongoing
PRJ-049 | Edo Retaining Wall Phase 2 | Retaining Wall | Edo | Apex Infra Ltd | CCECC Consult | 2020 | 582224000 | 722764000 | 140540000 | 36 | 44 | 8 | 81 | Contractor default | Ongoing
PRJ-050 | Edo Drainage System Phase 1 | Drainage System | Edo | Horizon Builders | AECOM Nigeria | 2022 | 1204191000 | 1623008000 | 418817000 | 17 | 25 | 8 | 47 | Equipment breakdown | Delayed

## Phase_Breakdown
Project_ID | Phase | Phase_Budget_NGN | Phase_Actual_NGN | Phase_Overrun_NGN | Phase_Overrun_Pct
PRJ-001 | Design | 25768000 | 23969000 | -1799000 | -7
PRJ-001 | Procurement | 38652000 | 43579000 | 4927000 | 12.7
PRJ-001 | Mobilisation | 16105000 | 16540000 | 435000 | 2.7
PRJ-001 | Construction | 193259000 | 211833000 | 18574000 | 9.6
PRJ-001 | Testing & Commissioning | 32210000 | 43701000 | 11491000 | 35.7
PRJ-001 | Handover | 16105000 | 18158000 | 2053000 | 12.7
PRJ-002 | Design | 8140000 | 10999000 | 2859000 | 35.1
PRJ-002 | Procurement | 12209000 | 17082000 | 4873000 | 39.9
PRJ-002 | Mobilisation | 5087000 | 5348000 | 261000 | 5.1
PRJ-002 | Construction | 61047000 | 57942000 | -3105000 | -5.1
PRJ-002 | Testing & Commissioning | 10174000 | 9275000 | -899000 | -8.8
PRJ-002 | Handover | 5087000 | 6225000 | 1138000 | 22.4
PRJ-003 | Design | 28255000 | 42381000 | 14126000 | 50
PRJ-003 | Procurement | 42382000 | 47043000 | 4661000 | 11
PRJ-003 | Mobilisation | 17659000 | 22782000 | 5123000 | 29
PRJ-003 | Construction | 211911000 | 290051000 | 78140000 | 36.9
PRJ-003 | Testing & Commissioning | 35318000 | 45597000 | 10279000 | 29.1
PRJ-003 | Handover | 17659000 | 23885000 | 6226000 | 35.3
PRJ-004 | Design | 87652000 | 128828000 | 41176000 | 47
PRJ-004 | Procurement | 131477000 | 134056000 | 2579000 | 2
PRJ-004 | Mobilisation | 54782000 | 49974000 | -4808000 | -8.8
PRJ-004 | Construction | 657387000 | 651753000 | -5634000 | -0.9
PRJ-004 | Testing & Commissioning | 109564000 | 106905000 | -2659000 | -2.4
PRJ-004 | Handover | 54782000 | 71308000 | 16526000 | 30.2
PRJ-005 | Design | 124599000 | 154301000 | 29702000 | 23.8
PRJ-005 | Procurement | 186898000 | 192650000 | 5752000 | 3.1
PRJ-005 | Mobilisation | 77874000 | 102769000 | 24895000 | 32
PRJ-005 | Construction | 934490000 | 1271036000 | 336546000 | 36
PRJ-005 | Testing & Commissioning | 155748000 | 155853000 | 105000 | 0.1
PRJ-005 | Handover | 77874000 | 98460000 | 20586000 | 26.4
PRJ-006 | Design | 108547000 | 146403000 | 37856000 | 34.9
PRJ-006 | Procurement | 162821000 | 157728000 | -5093000 | -3.1
PRJ-006 | Mobilisation | 67842000 | 94408000 | 26566000 | 39.2
PRJ-006 | Construction | 814105000 | 1203925000 | 389820000 | 47.9
PRJ-006 | Testing & Commissioning | 135684000 | 130916000 | -4768000 | -3.5
PRJ-006 | Handover | 67842000 | 62103000 | -5739000 | -8.5
PRJ-007 | Design | 158366000 | 172171000 | 13805000 | 8.7
PRJ-007 | Procurement | 237549000 | 310336000 | 72787000 | 30.6
PRJ-007 | Mobilisation | 98979000 | 145984000 | 47005000 | 47.5
PRJ-007 | Construction | 1187743000 | 1351643000 | 163900000 | 13.8
PRJ-007 | Testing & Commissioning | 197957000 | 263087000 | 65130000 | 32.9
PRJ-007 | Handover | 98979000 | 93594000 | -5385000 | -5.4
PRJ-008 | Design | 36913000 | 48517000 | 11604000 | 31.4
PRJ-008 | Procurement | 55370000 | 70671000 | 15301000 | 27.6
PRJ-008 | Mobilisation | 23071000 | 22174000 | -897000 | -3.9
PRJ-008 | Construction | 276850000 | 377482000 | 100632000 | 36.3
PRJ-008 | Testing & Commissioning | 46142000 | 65068000 | 18926000 | 41
PRJ-008 | Handover | 23071000 | 29075000 | 6004000 | 26
PRJ-009 | Design | 120218000 | 116928000 | -3290000 | -2.7
PRJ-009 | Procurement | 180327000 | 268743000 | 88416000 | 49
PRJ-009 | Mobilisation | 75136000 | 102905000 | 27769000 | 37
PRJ-009 | Construction | 901637000 | 999304000 | 97667000 | 10.8
PRJ-009 | Testing & Commissioning | 150273000 | 173870000 | 23597000 | 15.7
PRJ-009 | Handover | 75136000 | 84328000 | 9192000 | 12.2
PRJ-010 | Design | 138332000 | 166493000 | 28161000 | 20.4
PRJ-010 | Procurement | 207498000 | 229231000 | 21733000 | 10.5
PRJ-010 | Mobilisation | 86458000 | 121884000 | 35426000 | 41
PRJ-010 | Construction | 1037491000 | 1445638000 | 408147000 | 39.3
PRJ-010 | Testing & Commissioning | 172915000 | 166573000 | -6342000 | -3.7
PRJ-010 | Handover | 86458000 | 127653000 | 41195000 | 47.6
PRJ-011 | Design | 43221000 | 55381000 | 12160000 | 28.1
PRJ-011 | Procurement | 64831000 | 90583000 | 25752000 | 39.7
PRJ-011 | Mobilisation | 27013000 | 35776000 | 8763000 | 32.4
PRJ-011 | Construction | 324155000 | 376439000 | 52284000 | 16.1
PRJ-011 | Testing & Commissioning | 54026000 | 72410000 | 18384000 | 34
PRJ-011 | Handover | 27013000 | 39960000 | 12947000 | 47.9
PRJ-012 | Design | 74781000 | 79421000 | 4640000 | 6.2
PRJ-012 | Procurement | 112171000 | 155348000 | 43177000 | 38.5
PRJ-012 | Mobilisation | 46738000 | 57156000 | 10418000 | 22.3
PRJ-012 | Construction | 560857000 | 667475000 | 106618000 | 19
PRJ-012 | Testing & Commissioning | 93476000 | 108558000 | 15082000 | 16.1
PRJ-012 | Handover | 46738000 | 62564000 | 15826000 | 33.9
PRJ-013 | Design | 62331000 | 66136000 | 3805000 | 6.1
PRJ-013 | Procurement | 93496000 | 131925000 | 38429000 | 41.1
PRJ-013 | Mobilisation | 38957000 | 54479000 | 15522000 | 39.8
PRJ-013 | Construction | 467479000 | 445039000 | -22440000 | -4.8
PRJ-013 | Testing & Commissioning | 77913000 | 111336000 | 33423000 | 42.9
PRJ-013 | Handover | 38957000 | 40761000 | 1804000 | 4.6
PRJ-014 | Design | 41576000 | 49011000 | 7435000 | 17.9
PRJ-014 | Procurement | 62364000 | 78965000 | 16601000 | 26.6
PRJ-014 | Mobilisation | 25985000 | 29295000 | 3310000 | 12.7
PRJ-014 | Construction | 311820000 | 286008000 | -25812000 | -8.3
PRJ-014 | Testing & Commissioning | 51970000 | 73307000 | 21337000 | 41.1
PRJ-014 | Handover | 25985000 | 26222000 | 237000 | 0.9
PRJ-015 | Design | 45349000 | 46586000 | 1237000 | 2.7
PRJ-015 | Procurement | 68023000 | 93783000 | 25760000 | 37.9
PRJ-015 | Mobilisation | 28343000 | 31296000 | 2953000 | 10.4
PRJ-015 | Construction | 340116000 | 485751000 | 145635000 | 42.8
PRJ-015 | Testing & Commissioning | 56686000 | 74866000 | 18180000 | 32.1
PRJ-015 | Handover | 28343000 | 30207000 | 1864000 | 6.6
PRJ-016 | Design | 74432000 | 67442000 | -6990000 | -9.4
PRJ-016 | Procurement | 111648000 | 163993000 | 52345000 | 46.9
PRJ-016 | Mobilisation | 46520000 | 44258000 | -2262000 | -4.9
PRJ-016 | Construction | 558239000 | 743599000 | 185360000 | 33.2
PRJ-016 | Testing & Commissioning | 93040000 | 111010000 | 17970000 | 19.3
PRJ-016 | Handover | 46520000 | 63030000 | 16510000 | 35.5
PRJ-017 | Design | 14514000 | 19077000 | 4563000 | 31.4
PRJ-017 | Procurement | 21772000 | 28032000 | 6260000 | 28.8
PRJ-017 | Mobilisation | 9072000 | 10836000 | 1764000 | 19.4
PRJ-017 | Construction | 108859000 | 149764000 | 40905000 | 37.6
PRJ-017 | Testing & Commissioning | 18143000 | 17342000 | -801000 | -4.4
PRJ-017 | Handover | 9072000 | 9371000 | 299000 | 3.3
PRJ-018 | Design | 93889000 | 123471000 | 29582000 | 31.5
PRJ-018 | Procurement | 140834000 | 152625000 | 11791000 | 8.4
PRJ-018 | Mobilisation | 58681000 | 73289000 | 14608000 | 24.9
PRJ-018 | Construction | 704168000 | 833704000 | 129536000 | 18.4
PRJ-018 | Testing & Commissioning | 117361000 | 143011000 | 25650000 | 21.9
PRJ-018 | Handover | 58681000 | 67794000 | 9113000 | 15.5
PRJ-019 | Design | 138759000 | 186986000 | 48227000 | 34.8
PRJ-019 | Procurement | 208138000 | 228634000 | 20496000 | 9.8
PRJ-019 | Mobilisation | 86724000 | 114624000 | 27900000 | 32.2
PRJ-019 | Construction | 1040689000 | 1105784000 | 65095000 | 6.3
PRJ-019 | Testing & Commissioning | 173448000 | 182266000 | 8818000 | 5.1
PRJ-019 | Handover | 86724000 | 84330000 | -2394000 | -2.8
PRJ-020 | Design | 69814000 | 70900000 | 1086000 | 1.6
PRJ-020 | Procurement | 104720000 | 101760000 | -2960000 | -2.8
PRJ-020 | Mobilisation | 43633000 | 53299000 | 9666000 | 22.2
PRJ-020 | Construction | 523601000 | 710691000 | 187090000 | 35.7
PRJ-020 | Testing & Commissioning | 87267000 | 88235000 | 968000 | 1.1
PRJ-020 | Handover | 43633000 | 44935000 | 1302000 | 3
PRJ-021 | Design | 148513000 | 176808000 | 28295000 | 19.1
PRJ-021 | Procurement | 222770000 | 297342000 | 74572000 | 33.5
PRJ-021 | Mobilisation | 92821000 | 137929000 | 45108000 | 48.6
PRJ-021 | Construction | 1113850000 | 1353085000 | 239235000 | 21.5
PRJ-021 | Testing & Commissioning | 185642000 | 198600000 | 12958000 | 7
PRJ-021 | Handover | 92821000 | 89137000 | -3684000 | -4
PRJ-022 | Design | 45372000 | 46119000 | 747000 | 1.6
PRJ-022 | Procurement | 68058000 | 70541000 | 2483000 | 3.6
PRJ-022 | Mobilisation | 28357000 | 28574000 | 217000 | 0.8
PRJ-022 | Construction | 340288000 | 309148000 | -31140000 | -9.2
PRJ-022 | Testing & Commissioning | 56715000 | 69220000 | 12505000 | 22
PRJ-022 | Handover | 28357000 | 30188000 | 1831000 | 6.5
PRJ-023 | Design | 13509000 | 20055000 | 6546000 | 48.5
PRJ-023 | Procurement | 20264000 | 24966000 | 4702000 | 23.2
PRJ-023 | Mobilisation | 8443000 | 11132000 | 2689000 | 31.8
PRJ-023 | Construction | 101320000 | 98865000 | -2455000 | -2.4
PRJ-023 | Testing & Commissioning | 16887000 | 23998000 | 7111000 | 42.1
PRJ-023 | Handover | 8443000 | 10085000 | 1642000 | 19.5
PRJ-024 | Design | 96825000 | 137843000 | 41018000 | 42.4
PRJ-024 | Procurement | 145238000 | 180740000 | 35502000 | 24.4
PRJ-024 | Mobilisation | 60516000 | 71508000 | 10992000 | 18.2
PRJ-024 | Construction | 726191000 | 845491000 | 119300000 | 16.4
PRJ-024 | Testing & Commissioning | 121032000 | 122317000 | 1285000 | 1.1
PRJ-024 | Handover | 60516000 | 56330000 | -4186000 | -6.9
PRJ-025 | Design | 92175000 | 135003000 | 42828000 | 46.5
PRJ-025 | Procurement | 138263000 | 164068000 | 25805000 | 18.7
PRJ-025 | Mobilisation | 57610000 | 80266000 | 22656000 | 39.3
PRJ-025 | Construction | 691316000 | 788394000 | 97078000 | 14
PRJ-025 | Testing & Commissioning | 115219000 | 108819000 | -6400000 | -5.6
PRJ-025 | Handover | 57610000 | 73606000 | 15996000 | 27.8
PRJ-026 | Design | 148927000 | 138825000 | -10102000 | -6.8
PRJ-026 | Procurement | 223390000 | 221049000 | -2341000 | -1
PRJ-026 | Mobilisation | 93079000 | 115204000 | 22125000 | 23.8
PRJ-026 | Construction | 1116952000 | 1208879000 | 91927000 | 8.2
PRJ-026 | Testing & Commissioning | 186159000 | 278559000 | 92400000 | 49.6
PRJ-026 | Handover | 93079000 | 90386000 | -2693000 | -2.9
PRJ-027 | Design | 141415000 | 192136000 | 50721000 | 35.9
PRJ-027 | Procurement | 212122000 | 268078000 | 55956000 | 26.4
PRJ-027 | Mobilisation | 88384000 | 121479000 | 33095000 | 37.4
PRJ-027 | Construction | 1060611000 | 1098170000 | 37559000 | 3.5
PRJ-027 | Testing & Commissioning | 176768000 | 214516000 | 37748000 | 21.4
PRJ-027 | Handover | 88384000 | 103437000 | 15053000 | 17
PRJ-028 | Design | 50703000 | 59101000 | 8398000 | 16.6
PRJ-028 | Procurement | 76055000 | 107701000 | 31646000 | 41.6
PRJ-028 | Mobilisation | 31689000 | 47344000 | 15655000 | 49.4
PRJ-028 | Construction | 380273000 | 411922000 | 31649000 | 8.3
PRJ-028 | Testing & Commissioning | 63379000 | 80657000 | 17278000 | 27.3
PRJ-028 | Handover | 31689000 | 40111000 | 8422000 | 26.6
PRJ-029 | Design | 35761000 | 48065000 | 12304000 | 34.4
PRJ-029 | Procurement | 53642000 | 78776000 | 25134000 | 46.9
PRJ-029 | Mobilisation | 22351000 | 22902000 | 551000 | 2.5
PRJ-029 | Construction | 268209000 | 275347000 | 7138000 | 2.7
PRJ-029 | Testing & Commissioning | 44702000 | 57945000 | 13243000 | 29.6
PRJ-029 | Handover | 22351000 | 22222000 | -129000 | -0.6
PRJ-030 | Design | 124295000 | 124828000 | 533000 | 0.4
PRJ-030 | Procurement | 186442000 | 176195000 | -10247000 | -5.5
PRJ-030 | Mobilisation | 77684000 | 70040000 | -7644000 | -9.8
PRJ-030 | Construction | 932209000 | 1090966000 | 158757000 | 17
PRJ-030 | Testing & Commissioning | 155368000 | 195187000 | 39819000 | 25.6
PRJ-030 | Handover | 77684000 | 83491000 | 5807000 | 7.5
PRJ-031 | Design | 151428000 | 157316000 | 5888000 | 3.9
PRJ-031 | Procurement | 227142000 | 300775000 | 73633000 | 32.4
PRJ-031 | Mobilisation | 94642000 | 125097000 | 30455000 | 32.2
PRJ-031 | Construction | 1135709000 | 1331527000 | 195818000 | 17.2
PRJ-031 | Testing & Commissioning | 189285000 | 248423000 | 59138000 | 31.2
PRJ-031 | Handover | 94642000 | 137642000 | 43000000 | 45.4
PRJ-032 | Design | 60886000 | 83578000 | 22692000 | 37.3
PRJ-032 | Procurement | 91328000 | 116446000 | 25118000 | 27.5
PRJ-032 | Mobilisation | 38054000 | 49345000 | 11291000 | 29.7
PRJ-032 | Construction | 456642000 | 666789000 | 210147000 | 46
PRJ-032 | Testing & Commissioning | 76107000 | 87910000 | 11803000 | 15.5
PRJ-032 | Handover | 38054000 | 46682000 | 8628000 | 22.7
PRJ-033 | Design | 120918000 | 155813000 | 34895000 | 28.9
PRJ-033 | Procurement | 181378000 | 262100000 | 80722000 | 44.5
PRJ-033 | Mobilisation | 75574000 | 105500000 | 29926000 | 39.6
PRJ-033 | Construction | 906889000 | 855057000 | -51832000 | -5.7
PRJ-033 | Testing & Commissioning | 151148000 | 151081000 | -67000 | 0
PRJ-033 | Handover | 75574000 | 81965000 | 6391000 | 8.5
PRJ-034 | Design | 28835000 | 38909000 | 10074000 | 34.9
PRJ-034 | Procurement | 43252000 | 53698000 | 10446000 | 24.2
PRJ-034 | Mobilisation | 18022000 | 19341000 | 1319000 | 7.3
PRJ-034 | Construction | 216262000 | 210772000 | -5490000 | -2.5
PRJ-034 | Testing & Commissioning | 36044000 | 47333000 | 11289000 | 31.3
PRJ-034 | Handover | 18022000 | 23786000 | 5764000 | 32
PRJ-035 | Design | 7692000 | 11273000 | 3581000 | 46.6
PRJ-035 | Procurement | 11538000 | 13849000 | 2311000 | 20
PRJ-035 | Mobilisation | 4807000 | 5751000 | 944000 | 19.6
PRJ-035 | Construction | 57688000 | 54704000 | -2984000 | -5.2
PRJ-035 | Testing & Commissioning | 9615000 | 8883000 | -732000 | -7.6
PRJ-035 | Handover | 4807000 | 5572000 | 765000 | 15.9
PRJ-036 | Design | 21993000 | 24047000 | 2054000 | 9.3
PRJ-036 | Procurement | 32990000 | 34647000 | 1657000 | 5
PRJ-036 | Mobilisation | 13746000 | 13125000 | -621000 | -4.5
PRJ-036 | Construction | 164950000 | 243655000 | 78705000 | 47.7
PRJ-036 | Testing & Commissioning | 27492000 | 38532000 | 11040000 | 40.2
PRJ-036 | Handover | 13746000 | 17115000 | 3369000 | 24.5
PRJ-037 | Design | 98569000 | 144943000 | 46374000 | 47
PRJ-037 | Procurement | 147853000 | 221742000 | 73889000 | 50
PRJ-037 | Mobilisation | 61605000 | 80294000 | 18689000 | 30.3
PRJ-037 | Construction | 739264000 | 784881000 | 45617000 | 6.2
PRJ-037 | Testing & Commissioning | 123211000 | 113864000 | -9347000 | -7.6
PRJ-037 | Handover | 61605000 | 83398000 | 21793000 | 35.4
PRJ-038 | Design | 60819000 | 71906000 | 11087000 | 18.2
PRJ-038 | Procurement | 91228000 | 117767000 | 26539000 | 29.1
PRJ-038 | Mobilisation | 38012000 | 55104000 | 17092000 | 45
PRJ-038 | Construction | 456139000 | 460196000 | 4057000 | 0.9
PRJ-038 | Testing & Commissioning | 76023000 | 95120000 | 19097000 | 25.1
PRJ-038 | Handover | 38012000 | 48688000 | 10676000 | 28.1
PRJ-039 | Design | 90488000 | 108136000 | 17648000 | 19.5
PRJ-039 | Procurement | 135732000 | 129590000 | -6142000 | -4.5
PRJ-039 | Mobilisation | 56555000 | 62707000 | 6152000 | 10.9
PRJ-039 | Construction | 678662000 | 746518000 | 67856000 | 10
PRJ-039 | Testing & Commissioning | 113110000 | 147278000 | 34168000 | 30.2
PRJ-039 | Handover | 56555000 | 80005000 | 23450000 | 41.5
PRJ-040 | Design | 48759000 | 53532000 | 4773000 | 9.8
PRJ-040 | Procurement | 73138000 | 96265000 | 23127000 | 31.6
PRJ-040 | Mobilisation | 30474000 | 32696000 | 2222000 | 7.3
PRJ-040 | Construction | 365689000 | 536508000 | 170819000 | 46.7
PRJ-040 | Testing & Commissioning | 60948000 | 84604000 | 23656000 | 38.8
PRJ-040 | Handover | 30474000 | 37485000 | 7011000 | 23
PRJ-041 | Design | 107561000 | 126158000 | 18597000 | 17.3
PRJ-041 | Procurement | 161342000 | 175655000 | 14313000 | 8.9
PRJ-041 | Mobilisation | 67226000 | 73543000 | 6317000 | 9.4
PRJ-041 | Construction | 806709000 | 1195632000 | 388923000 | 48.2
PRJ-041 | Testing & Commissioning | 134452000 | 153612000 | 19160000 | 14.3
PRJ-041 | Handover | 67226000 | 81260000 | 14034000 | 20.9
PRJ-042 | Design | 157494000 | 235118000 | 77624000 | 49.3
PRJ-042 | Procurement | 236241000 | 305837000 | 69596000 | 29.5
PRJ-042 | Mobilisation | 98434000 | 120636000 | 22202000 | 22.6
PRJ-042 | Construction | 1181205000 | 1355963000 | 174758000 | 14.8
PRJ-042 | Testing & Commissioning | 196868000 | 199339000 | 2471000 | 1.3
PRJ-042 | Handover | 98434000 | 109957000 | 11523000 | 11.7
PRJ-043 | Design | 125434000 | 169821000 | 44387000 | 35.4
PRJ-043 | Procurement | 188150000 | 239937000 | 51787000 | 27.5
PRJ-043 | Mobilisation | 78396000 | 106305000 | 27909000 | 35.6
PRJ-043 | Construction | 940752000 | 961575000 | 20823000 | 2.2
PRJ-043 | Testing & Commissioning | 156792000 | 192781000 | 35989000 | 23
PRJ-043 | Handover | 78396000 | 114192000 | 35796000 | 45.7
PRJ-044 | Design | 53498000 | 62211000 | 8713000 | 16.3
PRJ-044 | Procurement | 80248000 | 105843000 | 25595000 | 31.9
PRJ-044 | Mobilisation | 33437000 | 32529000 | -908000 | -2.7
PRJ-044 | Construction | 401239000 | 595394000 | 194155000 | 48.4
PRJ-044 | Testing & Commissioning | 66873000 | 84616000 | 17743000 | 26.5
PRJ-044 | Handover | 33437000 | 34894000 | 1457000 | 4.4
PRJ-045 | Design | 121277000 | 120674000 | -603000 | -0.5
PRJ-045 | Procurement | 181916000 | 223848000 | 41932000 | 23.1
PRJ-045 | Mobilisation | 75798000 | 93334000 | 17536000 | 23.1
PRJ-045 | Construction | 909579000 | 869490000 | -40089000 | -4.4
PRJ-045 | Testing & Commissioning | 151596000 | 226690000 | 75094000 | 49.5
PRJ-045 | Handover | 75798000 | 109737000 | 33939000 | 44.8
PRJ-046 | Design | 40581000 | 47759000 | 7178000 | 17.7
PRJ-046 | Procurement | 60871000 | 59074000 | -1797000 | -3
PRJ-046 | Mobilisation | 25363000 | 35490000 | 10127000 | 39.9
PRJ-046 | Construction | 304357000 | 364932000 | 60575000 | 19.9
PRJ-046 | Testing & Commissioning | 50726000 | 67464000 | 16738000 | 33
PRJ-046 | Handover | 25363000 | 30571000 | 5208000 | 20.5
PRJ-047 | Design | 55618000 | 59181000 | 3563000 | 6.4
PRJ-047 | Procurement | 83426000 | 116866000 | 33440000 | 40.1
PRJ-047 | Mobilisation | 34761000 | 51729000 | 16968000 | 48.8
PRJ-047 | Construction | 417131000 | 436419000 | 19288000 | 4.6
PRJ-047 | Testing & Commissioning | 69522000 | 85565000 | 16043000 | 23.1
PRJ-047 | Handover | 34761000 | 39285000 | 4524000 | 13
PRJ-048 | Design | 151068000 | 219520000 | 68452000 | 45.3
PRJ-048 | Procurement | 226602000 | 273043000 | 46441000 | 20.5
PRJ-048 | Mobilisation | 94417000 | 134789000 | 40372000 | 42.8
PRJ-048 | Construction | 1133008000 | 1607077000 | 474069000 | 41.8
PRJ-048 | Testing & Commissioning | 188835000 | 201251000 | 12416000 | 6.6
PRJ-048 | Handover | 94417000 | 129729000 | 35312000 | 37.4
PRJ-049 | Design | 46578000 | 53517000 | 6939000 | 14.9
PRJ-049 | Procurement | 69867000 | 102044000 | 32177000 | 46.1
PRJ-049 | Mobilisation | 29111000 | 35068000 | 5957000 | 20.5
PRJ-049 | Construction | 349334000 | 486388000 | 137054000 | 39.2
PRJ-049 | Testing & Commissioning | 58222000 | 62280000 | 4058000 | 7
PRJ-049 | Handover | 29111000 | 31415000 | 2304000 | 7.9
PRJ-050 | Design | 96335000 | 120627000 | 24292000 | 25.2
PRJ-050 | Procurement | 144503000 | 216659000 | 72156000 | 49.9
PRJ-050 | Mobilisation | 60210000 | 71878000 | 11668000 | 19.4
PRJ-050 | Construction | 722515000 | 714681000 | -7834000 | -1.1
PRJ-050 | Testing & Commissioning | 120419000 | 147290000 | 26871000 | 22.3
PRJ-050 | Handover | 60210000 | 66657000 | 6447000 | 10.7

## Contractor_Scorecard
Contractor | Projects_Handled | Total_Budget_NGN | Total_Actual_NGN | Avg_Cost_Overrun_Pct | Avg_Planned_Duration | Avg_Actual_Duration | Delay_Rate_Pct | Performance_Score
Pioneer Builders Ltd | 8 | 8100351000 | 11541559000 | 42.5 | 30.8 | 39.1 | 100 | 0
Apex Infra Ltd | 2 | 683969000 | 831560000 | 21.6 | 41 | 52 | 100 | 0
Grandeur Works | 6 | 5365012000 | 6373825000 | 18.8 | 32.7 | 42.7 | 100 | 0
BuildRight Nig Ltd | 6 | 6141159000 | 8161160000 | 32.9 | 24.3 | 31.3 | 100 | 0
Nile Construction | 4 | 4650451000 | 5635945000 | 21.2 | 26 | 38.8 | 100 | 0
Greenfield Eng Ltd | 5 | 6298809000 | 8065462000 | 28 | 36.6 | 49.4 | 100 | 0
Mainland Const. Co. | 3 | 1766405000 | 2103045000 | 19.1 | 28.3 | 43.3 | 100 | 0
Horizon Builders | 10 | 9565520000 | 12572607000 | 31.4 | 28.3 | 40.8 | 100 | 0
Tetrazzini & Sons Ltd | 4 | 5584073000 | 7437404000 | 33.2 | 20 | 25.5 | 100 | 0
Fedex Const. Co. | 2 | 2328990000 | 2844503000 | 22.1 | 29.5 | 41.5 | 100 | 0

## Data_Dictionary
Table | Column | Data Type | Description
▶ Projects
| Project_ID | TEXT | Unique identifier for each project (e.g. PRJ-001)
| Project_Name | TEXT | Descriptive name: State + Type + Phase
| Project_Type | TEXT | Category of infrastructure project
| State | TEXT | Nigerian state where project is located
| Contractor | TEXT | Name of the main contractor
| Consultant | TEXT | Supervising consultant firm
| Year_Start | INTEGER | Year the project commenced
| Budget_NGN | CURRENCY | Original approved project budget (Naira)
| Actual_Cost_NGN | CURRENCY | Final or current actual expenditure (Naira)
| Cost_Overrun_NGN | CURRENCY | Actual Cost minus Budget (positive = overrun)
| Planned_Duration_Months | INTEGER | Original planned project duration in months
| Actual_Duration_Months | INTEGER | Actual or projected completion duration
| Schedule_Delay_Months | INTEGER | Actual minus Planned duration (positive = delay)
| Pct_Complete | INTEGER | Percentage of work completed (0–100)
| Primary_Delay_Reason | TEXT | Main recorded reason for schedule delay
| Status | TEXT | Project status: Completed / Ongoing / Delayed
▶ Phase_Breakdown
| Project_ID | TEXT | Foreign key linking to Projects table
| Phase | TEXT | Project phase name (Design, Procurement, etc.)
| Phase_Budget_NGN | CURRENCY | Allocated budget for this phase
| Phase_Actual_NGN | CURRENCY | Actual spend for this phase
| Phase_Overrun_NGN | CURRENCY | Phase overrun in Naira
| Phase_Overrun_Pct | DECIMAL | Phase overrun as percentage of phase budget
▶ Contractor_Scorecard
| Contractor | TEXT | Contractor name (primary key)
| Projects_Handled | INTEGER | Total number of projects awarded
| Total_Budget_NGN | CURRENCY | Sum of all project budgets
| Total_Actual_NGN | CURRENCY | Sum of all actual costs
| Avg_Cost_Overrun_Pct | DECIMAL | Average cost overrun % across all projects
| Avg_Planned_Duration | DECIMAL | Average planned project duration in months
| Avg_Actual_Duration | DECIMAL | Average actual project duration in months
| Delay_Rate_Pct | DECIMAL | % of projects with schedule delays
| Performance_Score | DECIMAL | Composite score: 100 minus overrun & delay rates